## F4.2
(Rs. Crore)
<Name of the Generating Company / Business>
MYT Petition Formats - Generation
Form 4.3: Capital Work-in-progress - Project-wise details
| Project Details | [51 empty] | FY2017-18 | [10 empty] | FY2018-19 | [6 empty] | 19-20 | [7 empty] | 20-21 | [6 empty] | 21-22 | [6 empty] | FY2022-23 | [6 empty] | FY2023-24 | [6 empty] | FY2024-25
| Sr. No. | DPR Nos. | In Progress/Completed | Project Benefits | Project Description | MERC Approval No. | MERC Approval Date | Approved Project Cost | Debt Equity Ratio | Grant Funding | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [8 empty] | Physical Progress (%) | [8 empty] | Capitalisation (W/O IDC) | [8 empty] | Reasons for Delay, if any | [7 empty] | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Op. CWIP 01.04.2017 | Investment during the year | Capital Work in Progress |  |  |  | Cl. CWIP_31.03.2018 |  |  | Cumulative Expenditure Incurred till beginning of the Year | Capital Expenditure Capitalised | Op. CWIP 01.04.2018 | Investment during the year | Capital Work in Progress |  |  |  | Cl.CWIP 31.03.2019 | Op.CWIP 01.04.2019 | Investment during the year |  | 19-20 | [6 empty] | 20-21 | [6 empty] | 21-22 | [6 empty] | 22-23 | [6 empty] | 23-24 | [6 empty] | 24-25 |  |  |  |  | 20-21 | 21-22 | 22-23 | 23-24 | 24-25
[16 empty] | Actual Capex till FY 2021-22 |  |  | Estimated | Projected |  |  |  |  | Actual Progress till FY 2021-22 | Actual |  | Estimated | Projected |  |  |  |  | Actual Capitalisation till FY 2021-22 | Actual |  | Estimated | Projected |  |  |  |  | Change in Scope of Work | Physical Progress Remark | Any other reason | [12 empty] | 17-18 | [10 empty] | 18-19 |  |  |  | SK MAIL
[17 empty] | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 |  | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 |  | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | [12 empty] | Works Capitalised | Interest Capitalised-IDC | Expenses Capitalised | Total Capitalisation | [7 empty] | Works Capitalised | Expenses Capitalised-Staff Cost | Interest Capitalised-IDC | Total Capitalisation |  |  |  |  | Works Capitalised | Expenses Capitalised-Staff Cost | Interest Capitalised-IDC | Total Capitalisation |  |  |  | Works Capitalised | Expenses Capitalised-Staff Cost | Interest Capitalised-IDC | Total Capitalisation |  |  |  | Works Capitalised | Expenses Capitalised-Staff Cost | Interest Capitalised-IDC | Projected Capitalisation |  |  |  | Works Capitalised | Expenses Capitalised-Staff Cost | Interest Capitalised-IDC | Projected Capitalisation |  |  |  | Works Capitalised | Expenses Capitalised-Staff Cost | Interest Capitalised-IDC | Projected Capitalisation |  |  |  | Works Capitalised | Expenses Capitalised-Staff Cost | Interest Capitalised-IDC | Total Capitalisation | Projected Capitalisation | Projected Capitalisation | Projected Capitalisation | Projected Capitalisation | Projected Capitalisation | Projected Capitalisation
|  | a) DPR Schemes | [5 empty] | 518.3
(i) In-principle approved by MERC
| 1 | RINFRA-G/DPR/FY10/1 |  |  | Renovation & Modernization, Reliability Improvement And Miscellaneous Projects At DTPS | MERC/CAPEX/20102011/02594 | 2011-03-31 | 25.96 | 70:30 |  | FY 09-10 |  |  |  |  | 23.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.85% | 91.85% | 91.85% | 91.85% | 91.85% | 91.85% | 91.85% | 91.85% | 91.85% | 23.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 19.2935 | 18.9404 | 0.177 | 0 | 1.1235 | 0.025384 | 0 | 1.1488 | 0.15189 |  |  | 0.76 | 0.76 | 0.15189 |  | 0.64795 | 0.034282 | 0.040141 | 0.72237 | 0 | 0 | 1.62 | 237 | 1.62 | 0 | 0 | 1.62 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0.3 | 0 | 0
| 1.1 | RINFRA-G/DPR/FY10/1.1 | Completed | Reliability Improvement | Up-gradation of Unit # 2 UPS, 48V Switchyard Battery System and +/- 24V Battery to improve reliability of power supply back-up systems | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.85 | 70:30 |  | FY 09-10 | FY 09-10 | FY 13-14 | FY 19-20 | 1. Reliability Improvement 2. Technology Upgradation 3. Efficiency Improvement 4. To encountered obsolescence 5. Safety Enhancement | 0.76 | FY23: 0; FY24: 0; Estimated FY25: 0 | 89.41% | 89.41% | 89.41% | 89.41% | 89.41% | 89.41% | 89.41% | 89.41% | 89.41% | 0.76 | 0 | 0 | 0 | [13 empty] | 0.76 | 0.76 | 0 |  |  |  |  | 0 |  |  |  | 0.76 | 0.76 | 0 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.2 | RINFRA-G/DPR/FY10/1.2 | Completed | Reliability Improvement | Up-gradation of existing relay based control system Ash Pump House to PLC based system and Upgradation of PLC systems of Condensate Polishing Unit (CPU) and Hydrogen Drier | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.35 | 70:30 | [6 empty] | 0.50794 | FY23: 0; FY24: 0; Estimated FY25: 0 | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 0.50794 | 0 | 0 | 0 | [13 empty] | 0.19095 | 0.19095 | 0 |  |  |  |  | 0 | [7 empty] | 0.26007 | 0.034282 | 0.023591 | 0.31794 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0
15 | 1.3 | RINFRA-G/DPR/FY10/1.3 | Completed | Obsolence | Modernization and Up-gradation of Electronic Cards of PR05 Module, BK03C Module, EB02 & EA02 Cards for improving reliability of the system and plant | MERC/CAPEX/20102011/02594 | 2011-03-31 | 4 | 70:30 | [6 empty] | 3.803 | FY23: 0; FY24: 0; Estimated FY25: 0 | 95.08% | 95.08% | 95.08% | 95.08% | 95.08% | 95.08% | 95.08% | 95.08% | 95.08% | 3.803 | 0 | 0 | 0 | [13 empty] | 2.5317 | 2.5317 | 0 |  |  |  |  | 0 | [13 empty] | 1.37 | 9 | 1.37 |  |  | 1.37 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.4 | RINFRA-G/DPR/FY10/1.4 | Completed | Safety Improvement | Upgradation of Fire Alarm and CCTV system for enhancing safety and security of personnel and plant | MERC/CAPEX/20102011/02594 | 2011-03-31 | 1.6 | 70:30 | [6 empty] | 1.5886 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.29% | 99.29% | 99.29% | 99.29% | 99.29% | 99.29% | 99.29% | 99.29% | 99.29% | 1.5886 | 0 | 0 | 0 | [13 empty] | 1.5878 | 1.5878 | 0 |  | 0.0008015 | 6.0173e-05 |  | 0.00086167 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.5 | RINFRA-G/DPR/FY10/1.5 | Completed | Efficiency Improvement | Up-gradation of Secondary Air Damper Control (SADC) to optimize excess air and efficiency of the plant. | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.1 | 70:30 | [6 empty] | 0.085086 | FY23: 0; FY24: 0; Estimated FY25: 0 | 85.09% | 85.09% | 85.09% | 85.09% | 85.09% | 85.09% | 85.09% | 85.09% | 85.09% | 0.085086 | 0 | 0 | 0 | [13 empty] | 0.085086 | 0.085086 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.6 | RINFRA-G/DPR/FY10/1.6 | Completed | Reliability Improvement | Installation of Flow transmitters at Condenser Cooling Water Inlet to optimize operations of condenser and CW system | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.12 | 70:30 | [6 empty] | 0.10414 | FY23: 0; FY24: 0; Estimated FY25: 0 | 86.78% | 86.78% | 86.78% | 86.78% | 86.78% | 86.78% | 86.78% | 86.78% | 86.78% | 0.10414 | 0 | 0 | 0 | [13 empty] | 0.10414 | 0.10414 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.7 | RINFRA-G/DPR/FY10/1.7 | Completed | Environment | Up-gradation of ESP Field Controller & Opacity Monitor for better monitoring of ESP performance and environmental parameters | MERC/CAPEX/20102011/02594 | 2011-03-31 | 1.66 | 70:30 | [6 empty] | 1.559 | FY23: 0; FY24: 0; Estimated FY25: 0 | 93.92% | 93.92% | 93.92% | 93.92% | 93.92% | 93.92% | 93.92% | 93.92% | 93.92% | 1.559 | 0 | 0 | 0 | [13 empty] | 1.5637 | 1.5637 | 0 |  | 0.1626 | 0.011445 |  | 0.17405 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.8 | RINFRA-G/DPR/FY10/1.8 | Completed | Reliability Improvement | Up-gradation of metering system in 220 kV system to meet accuracy requirements of CEA Regulations | MERC/CAPEX/20102011/02594 | 2011-03-31 | 1.12 | 70:30 | [6 empty] | 1.1093 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.04% | 99.04% | 99.04% | 99.04% | 99.04% | 99.04% | 99.04% | 99.04% | 99.04% | 1.1093 | 0 | 0 | 0 | [13 empty] | 1.2937 | 1.1167 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.9 | RINFRA-G/DPR/FY10/1.9 | Completed | Reliability Improvement | Up-gradation of 6.6kV Line PTs & Bus PTs to improved electrical Safety and reliability of system | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.2 | 70:30 | [6 empty] | 0.086582 | FY23: 0; FY24: 0; Estimated FY25: 0 | 43.29% | 43.29% | 43.29% | 43.29% | 43.29% | 43.29% | 43.29% | 43.29% | 43.29% | 0.086582 | 0 | 0 | 0 | [13 empty] | 0.086582 | 0.086582 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.1 | RINFRA-G/DPR/FY10/1.10 | Completed | Reliability Improvement | Purchase of Electrical Testing & Measuring Instruments for better diagnosis of electrical installations to improve safety, availability and reliability | MERC/CAPEX/20102011/02594 | 2011-03-31 | 1.03 | 70:30 | [6 empty] | 1.0265 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.66% | 99.66% | 99.66% | 99.66% | 99.66% | 99.66% | 99.66% | 99.66% | 99.66% | 1.0265 | 0 | 0 | 0 | [13 empty] | 0.26008 | 0.26008 | 0 |  | 0.59638 | 0 |  | 0.59638 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.11 | RINFRA-G/DPR/FY10/1.11 | Completed | Reliability Improvement | Up-gradation of LT Circuit Breakers to improve reliability of LT auxiliaries | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.33 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.12 | RINFRA-G/DPR/FY10/1.12 | Completed | Reliability Improvement | Replacement of old Stacker Reclaimer Transformer to improve availability of Stacker- Reclaimer and reliability of coal handling system | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.09 | 70:30 | [6 empty] | 0.072 | FY23: 0; FY24: 0; Estimated FY25: 0 | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 0.072 | 0 | 0 | 0 | [13 empty] | 0.072 | 0.072 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
145 | 1.13 | RINFRA-G/DPR/FY10/1.13 | Completed | Reliability Improvement | Purchase of new oil filtration machines for transformers to improve reliability | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.31 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | [7 empty] | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0.3 |  |  | 0.3 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0.3 | 0 | 0
70 | 1.14 | RINFRA-G/DPR/FY10/1.14 | Completed | Reliability Improvement | Modernization of 6.6 kV Protection Systems to improve safety, availability and reliability of 6.6 kV system and connected equipment. | MERC/CAPEX/20102011/02594 | 2011-03-31 | 2.09 | 70:30 | [6 empty] | 1.4456 | FY23: 0; FY24: 0; Estimated FY25: 0 | 69.17% | 69.17% | 69.17% | 69.17% | 69.17% | 69.17% | 69.17% | 69.17% | 69.17% | 1.4456 | 0 | 0 | 0 | [13 empty] | 1.0851 | 1.0851 | 0 |  |  |  |  | 0 | [13 empty] | 0.25 | 64 | 0.25 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 1.15 | RINFRA-G/DPR/FY10/1.15 | Completed | Obsolence | Replacement of Station Battery for Unit # 1 and Unit #2 and common stand-by to improve reliability of emergency power supply | MERC/CAPEX/20102011/02594 | 2011-03-31 | 1.85 | 70:30 | [6 empty] | 1.71 | FY23: 0; FY24: 0; Estimated FY25: 0 | 92.43% | 92.43% | 92.43% | 92.43% | 92.43% | 92.43% | 92.43% | 92.43% | 92.43% | 1.71 | 0 | 0 | 0 | [13 empty] | 1.71 | 1.71 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.16 | RINFRA-G/DPR/FY10/1.16 | Completed | Environment | Up-gradation of UPS of Ambient Air Quality Monitoring Stations for reliable monitoring of environmental parameters. | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.18 | 70:30 | [6 empty] | 0.12 | FY23: 0; FY24: 0; Estimated FY25: 0 | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 0.12 | 0 | 0 | 0 | [13 empty] | 0.12 | 0.12 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.17 | RINFRA-G/DPR/FY10/1.17 | Completed | Reliability Improvement | Purchase of Spare CW Pump Motor (6.6 KV 1260 KW) for improving reliability and availability of Cooling Water System | MERC/CAPEX/20102011/02594 | 2011-03-31 | 1.2 | 70:30 | [6 empty] | 1.29 | FY23: 0; FY24: 0; Estimated FY25: 0 | 107.5% | 107.5% | 107.5% | 107.5% | 107.5% | 107.5% | 107.5% | 107.5% | 107.5% | 1.29 | 0 | 0 | 0 | [13 empty] | 1.29 | 1.29 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.18 | RINFRA-G/DPR/FY10/1.18 | Completed | Reliability Improvement | Purchase of Spare Alternator for Diesel Locomotive for improving reliability of Coal Handling System | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.54 | 70:30 | [6 empty] | 0.51 | FY23: 0; FY24: 0; Estimated FY25: 0 | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 0.51 | 0 | 0 | 0 | [13 empty] | 0.51 | 0.51 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.19 | RINFRA-G/DPR/FY10/1.19 | Completed | Reliability Improvement | Up-gradation of Control System of Generator Transformer (GT) Cooler to improve reliability of GT | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.15 | 70:30 | [6 empty] | 0.1 | FY23: 0; FY24: 0; Estimated FY25: 0 | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 0.1 | 0 | 0 | 0 | [13 empty] | 0.094921 | 0.094921 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.2 | RINFRA-G/DPR/FY10/1.20 | Completed | Reliability Improvement | Procurement of common spare for Neutral Grounding Transformer (NGT) for Generator to improve the reliability of the Units | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.04 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.21 | RINFRA-G/DPR/FY10/1.21 | Completed | Efficiency Improvement | Renovation and Modernization of Air Pre-heater Heater (APH) of Unit #2 to improve efficiency of the Unit | MERC/CAPEX/20102011/02594 | 2011-03-31 | 3.4 | 70:30 | [6 empty] | 2.5778 | FY23: 0; FY24: 0; Estimated FY25: 0 | 75.82% | 75.82% | 75.82% | 75.82% | 75.82% | 75.82% | 75.82% | 75.82% | 75.82% | 2.5778 | 0 | 0 | 0 | [13 empty] | 2.5778 | 2.5778 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.22 | RINFRA-G/DPR/FY10/1.22 | Completed | Reliability Improvement | Reliability Improvement through replacement of Silencer assemblies of Primary Air Fan & Forced Draft fan in Unit 2 | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.6 | 70:30 | [6 empty] | 0.46 | FY23: 0; FY24: 0; Estimated FY25: 0 | 76.67% | 76.67% | 76.67% | 76.67% | 76.67% | 76.67% | 76.67% | 76.67% | 76.67% | 0.46 | 0 | 0 | 0 | [13 empty] | 0.46 | 0.46 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.23 | RINFRA-G/DPR/FY10/1.23 | Completed | Reliability Improvement | Procurement of Low Vacuum Dehydration (LVDH) Machine for recovery and recycling of spent lubrication oil from Turbine and Boiler Feed Pump (BFP) | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.27 | 70:30 | [6 empty] | 0.46298 | FY23: 0; FY24: 0; Estimated FY25: 0 | 171.5% | 171.5% | 171.5% | 171.5% | 171.5% | 171.5% | 171.5% | 171.5% | 171.5% | 0.46298 | 0 | 0 | 0 | [13 empty] | 0.38398 | 0.38398 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.24 | RINFRA-G/DPR/FY10/1.24 | Completed | Reliability Improvement | Replacement of Auxiliary Steam pressure control valve in Unit#2 (AS-22) for efficient utilization of steam | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.15 | 70:30 | [6 empty] | 0.06 | FY23: 0; FY24: 0; Estimated FY25: 0 | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 0.06 | 0 | 0 | 0 | [13 empty] | 0.06 | 0.06 | 0 |  | 0.0078505 | 0.00058939 |  | 0.0084399 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
31 | 1.25 | RINFRA-G/DPR/FY10/1.25 | Completed | Obsolence | Up-gradation of IT Infrastructure at DTPS | MERC/CAPEX/20102011/02594 | 2011-03-31 | 2.9 | 70:30 | [6 empty] | 2.7884 | FY23: 0; FY24: 0; Estimated FY25: 0 | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 2.7884 | 0 | 0 | 0 | [13 empty] | 0.84823 | 0.6721 | 0.177 |  | 0.35584 | 0.013289 |  | 0.36913 | 0.15189 |  |  |  |  | 0.15189 |  | 0.38788 | 0 | 0.01655 | 0.40443 |  |  | 0 | 25 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.9 |  |  | 0.9 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0.9 | 0 | 0 | 0 | 0
| 1.26 | RINFRA-G/DPR/FY10/1.26 | Completed | Obsolence | Procurement of Software (for auto back-up of data and Power Plant Performance Analysis) | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.5 | 70:30 | [6 empty] | 1.0973 | FY23: 0; FY24: 0; Estimated FY25: 0 | 219.5% | 219.5% | 219.5% | 219.5% | 219.5% | 219.5% | 219.5% | 219.5% | 219.5% | 1.0973 | 0 | 0 | 0 | [13 empty] | 1.0973 | 1.0973 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 1.27 | RINFRA-G/DPR/FY10/1.27 | Completed | Reliability Improvement | Office Modernization (Mechanical Maintenance Building in Service Building and CHP Maintenance Building) | MERC/CAPEX/20102011/02594 | 2011-03-31 | 0.33 | 70:30 | [6 empty] | 0.52052 | FY23: 0; FY24: 0; Estimated FY25: 0 | 157.7% | 157.7% | 157.7% | 157.7% | 157.7% | 157.7% | 157.7% | 157.7% | 157.7% | 0.52052 | 0 | 0 | 0 | [13 empty] | 0.52052 | 0.52052 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
[72 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| 2 | RINFRA-G/DPR/FY10/2 |  |  | Township Residential area renovation and Construction of Boundry wall | MERC/CAPEX/20112012/01686 | 2011-09-22 | 21.75 | 70:30 |  | FY 09-10 |  | FY 14-15 |  |  | 18.4845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84.99% | 84.99% | 84.99% | 84.99% | 84.99% | 84.99% | 84.99% | 84.99% | 84.99% | 18.4845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12.7099 | 12.8875 | 0.010051 | 0 | 2.0111 | 0.038425 | 0 | 2.0496 | 1.4903 |  |  | 0 | 0 | 1.4903 | 0 | 1.4845 | 0.12567 | 0.16175 | 1.7719 | 0.08726 | 0.08726 | 2.1127 | 192 | 2.2 | 0 | 0 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 4.4 | 0 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 0
11 | 2.1 | RINFRA-G/DPR/FY10/2.1 | Completed | Reliability Improvement | Township Residential area renovation | MERC/CAPEX/20112012/01686 | 2011-09-22 | 14.54 | 70:30 |  | FY 09-10 | FY 09-10 | FY 14-15 | FY 21-22 | 1. Safety Enhancement 2. Statutory Compliance | 15.674 | FY23: 0; FY24: 0; Estimated FY25: 0 | 107.8% | 107.8% | 107.8% | 107.8% | 107.8% | 107.8% | 107.8% | 107.8% | 107.8% | 15.674 | 0 | 0 | 0 | [13 empty] | 9.8816 | 9.9756 | 0.010051 |  | 2.0111 | 0.038425 |  | 2.0496 | 1.4903 |  |  |  |  | 1.4903 |  | 1.4845 | 0.12567 | 0.16175 | 1.7719 | 0.08726 | 0.08726 | 2.1127 | 5 | 2.2 |  |  | 2.2 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
180 | 2.2 | RINFRA-G/DPR/FY10/2.2 | Completed | Safety Improvement | Construction of Boundry wall | MERC/CAPEX/20112012/01686 | 2011-09-22 | 7.21 | 70:30 |  |  |  | FY 14-15 |  |  | 2.8105 | FY23: 0; FY24: 0; Estimated FY25: 0 | 38.98% | 38.98% | 38.98% | 38.98% | 38.98% | 38.98% | 38.98% | 38.98% | 38.98% | 2.8105 | 0 | 0 | 0 | [13 empty] | 2.8283 | 2.9118 | 0 |  |  |  |  | 0 | [13 empty] | 0 | 187 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 4.4 | 4.4 |  |  | 4.4 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 4.4 | 0 | 0
119 | [71 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 3 | RINFRA-G/DPR/FY11/1 |  |  | Bundled DPR for Non-DPR Capex Schemes of Renovation & Modernization Projects at DTPS for FY 2010-11 | MERC/Tech-IX/CAPEX/20122013/02772 | 2013-03-01 | 18.18 | 70:30 |  | FY 11-12 |  | FY 12-13 |  |  | 9.3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.64% | 51.64% | 51.64% | 51.64% | 51.64% | 51.64% | 51.64% | 51.64% | 51.64% | 9.3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 10.8683 | 10.8683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.1 | RINFRA-G/DPR/FY11/1.1 | Completed | Reliability Improvement | Reliability improvement thhrough upgradation of HP bypass & LP bypass system and turbovisory | MERC/Tech-IX/CAPEX/20122013/02772 | 2013-03-01 | 3.13 | 70:30 |  | FY 11-12 | FY 11-12 | FY 12-13 | FY 18-19 | 1. Reliability Improvement 2. Statutory Compliance 3. Efficiency Improvement | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | [7 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
153 | 3.2 | RINFRA-G/DPR/FY11/1.2 | Completed | Safety Improvement | Moderniosation of bus bar protection scheme for 220KV switchyard and protection scheme for 60MVA station transformer to improve electrical safety and reliability of the system | MERC/Tech-IX/CAPEX/20122013/02772 | 2013-03-01 | 1.14 | 70:30 | [6 empty] | 0.81659 | FY23: 0; FY24: 0; Estimated FY25: 0 | 71.63% | 71.63% | 71.63% | 71.63% | 71.63% | 71.63% | 71.63% | 71.63% | 71.63% | 0.81659 | 0 | 0 | 0 | [13 empty] | 0.81659 | 0.81659 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
103 | 3.3 | RINFRA-G/DPR/FY11/1.3 | Completed | Reliability Improvement | Replacement of Plate Heat Exchanger(PHE) plates for reliability improvement | MERC/Tech-IX/CAPEX/20122013/02772 | 2013-03-01 | 1.9 | 70:30 | [6 empty] | 1.9281 | FY23: 0; FY24: 0; Estimated FY25: 0 | 101.5% | 101.5% | 101.5% | 101.5% | 101.5% | 101.5% | 101.5% | 101.5% | 101.5% | 1.9281 | 0 | 0 | 0 | [13 empty] | 1.9281 | 1.9281 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
152 | 3.4 | RINFRA-G/DPR/FY11/1.4 | Completed | Reliability Improvement | Replacement of travelling water screen(TWS)intermediate section for reliability improvement | MERC/Tech-IX/CAPEX/20122013/02772 | 2013-03-01 | 1.04 | 70:30 | [6 empty] | 0.80548 | FY23: 0; FY24: 0; Estimated FY25: 0 | 77.45% | 77.45% | 77.45% | 77.45% | 77.45% | 77.45% | 77.45% | 77.45% | 77.45% | 0.80548 | 0 | 0 | 0 | [13 empty] | 0.90069 | 0.90069 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
151 | 3.5 | RINFRA-G/DPR/FY11/1.5 | Completed | Statutory Requirement | Procurement of booster fan rotor with shaft bearing assembly(Critical spare-FGD) | MERC/Tech-IX/CAPEX/20122013/02772 | 2013-03-01 | 7.97 | 70:30 | [6 empty] | 4.8162 | FY23: 0; FY24: 0; Estimated FY25: 0 | 60.43% | 60.43% | 60.43% | 60.43% | 60.43% | 60.43% | 60.43% | 60.43% | 60.43% | 4.8162 | 0 | 0 | 0 | [13 empty] | 7.223 | 7.223 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
150 | 3.6 | RINFRA-G/DPR/FY11/1.6 | Completed | Efficiency Improvement | Refurbishment of HP turbine module to improve heat rate | MERC/Tech-IX/CAPEX/20122013/02772 | 2013-03-01 | 3 | 70:30 | [6 empty] | 1.0225 | FY23: 0; FY24: 0; Estimated FY25: 0 | 34.08% | 34.08% | 34.08% | 34.08% | 34.08% | 34.08% | 34.08% | 34.08% | 34.08% | 1.0225 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
100 | 4 | RInfra-G/DPR/BP11-16/DPR No 1 |  |  | Renovation & Modernization Of Ash Handling System | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 21.2 | 70:30 |  | FY 11-12 |  | FY 15-16 |  |  | 12.2024 | 1.2881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.41% | 63.63% | 63.63% | 63.63% | 63.63% | 63.63% | 63.63% | 63.63% | 63.63% | 12.1707 | 1.3198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 3.4516 | 3.0406 | 0.2994 | 0 | 0.4588 | 0.029339 | 0 | 0.48814 | 0 |  |  | 0 | 0 | 0 | 0 | 0.5048 | 0.060344 | 0.023637 | 0.58879 | 0.15111 | 0.15111 | 2.1989 | 1305 | 2.35 | 0 | 0 | 2.35 | 0 | 0 | 0 | 3.35 | 0 | 0 | 3.35 | 0 | 0 | 0 | 2.7 | 0 | 0 | 2.7 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.35 | 2.7 | 3 | 0 | 0
149 | 4.1 | RInfra-G/DPR/BP11-16/DPR No 1.1 | Completed | Reliability Improvement/Statutory Compliance | Renovation of Dry ash conveying compressors & vent to improve reliability & energy conservation | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 3 | 70:30 |  | FY 11-12 | FY 11-12 | FY 15-16 | FY 21-22 | 1. Reliability Improvement | 0.74409 | FY23: 0.20032; FY24: 0; Estimated FY25: 0 | 24.8% | 31.48% | 31.48% | 31.48% | 31.48% | 31.48% | 31.48% | 31.48% | 31.48% | 0.74409 | 0.20032 | 0 | 0 | [13 empty] | 0.2235 | 0.2235 | 0 |  | 0.027648 | 0 |  | 0.027648 | [13 empty] | 0.5 | 237 | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  | 0 |  |  |  | 0.6 |  |  | 0.6 |  |  |  | 0.6 |  |  | 0.6 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0.6 | 0.6 | 0 | 0
26 | 4.2 | RInfra-G/DPR/BP11-16/DPR No 1.2 | Completed | Reliability Improvement/Statutory Compliance | Renovation of valves & piping to improve ash utilisation & reliability of the system | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 3 | 70:30 | [6 empty] | 2.1628 | FY23: 0.33057; FY24: 0; Estimated FY25: 0 | 71.04% | 83.11% | 83.11% | 83.11% | 83.11% | 83.11% | 83.11% | 83.11% | 83.11% | 2.1311 | 0.36224 | 0 | 0 | [13 empty] | 0.81353 | 0.77076 | 0.076056 |  | 0.28776 | 0.018574 |  | 0.30633 | [13 empty] | 0 | 164 | 0 |  |  | 0 |  |  |  | 0.6 |  |  | 0.6 |  |  |  | 0.5 |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.6 | 0.5 | 0.5 | 0 | 0
27 | 4.3 | RInfra-G/DPR/BP11-16/DPR No 1.3 | Completed | Reliability Improvement/Statutory Compliance | Procurement of classifier assemblies to improve ash utilization | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 1.7 | 70:30 | [6 empty] | 1.2048 | FY23: 0; FY24: 0; Estimated FY25: 0 | 70.87% | 70.87% | 70.87% | 70.87% | 70.87% | 70.87% | 70.87% | 70.87% | 70.87% | 1.2048 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [13 empty] | 0 | 166 | 0 |  |  | 0 |  |  |  | 0.75 |  |  | 0.75 |  |  |  | 0 |  |  | 0 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.75 | 0 | 0.5 | 0 | 0
101 | 4.4 | RInfra-G/DPR/BP11-16/DPR No 1.4 | Completed | Reliability Improvement/Statutory Compliance | Renovation of AHP pumps & clinker grinders for reliability & efficiency improvement of ash slurry transfer system | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 5.9 | 70:30 | [6 empty] | 3.2997 | FY23: 0; FY24: 0; Estimated FY25: 0 | 55.93% | 55.93% | 55.93% | 55.93% | 55.93% | 55.93% | 55.93% | 55.93% | 55.93% | 3.2997 | 0 | 0 | 0 | [13 empty] | 0.88073 | 0.88073 | 0 |  |  |  |  | 0 | [7 empty] | 0.18704 | 0.024655 | 0 | 0.2117 |  |  | 0 | 241 | 0 |  |  | 0 |  |  |  | 1.2 |  |  | 1.2 |  |  |  | 0.8 |  |  | 0.8 |  |  |  | 0.6 |  |  | 0.6 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 1.2 | 0.8 | 0.6 | 0 | 0
12 | 4.5 | RInfra-G/DPR/BP11-16/DPR No 1.5 | Completed | Reliability Improvement/Statutory Compliance | Installation of ash slurry pipe line at higher elevation in ash pond area | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 0.5 | 70:30 | [6 empty] | 0.42248 | FY23: 0; FY24: 0; Estimated FY25: 0 | 84.5% | 84.5% | 84.5% | 84.5% | 84.5% | 84.5% | 84.5% | 84.5% | 84.5% | 0.42248 | 0 | 0 | 0 | [13 empty] | 0.42248 | 0.27909 | 0.14339 |  | 0.14339 | 0.010765 |  | 0.15415 | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
28 | 4.6 | RInfra-G/DPR/BP11-16/DPR No 1.6 | Completed | Reliability Improvement/Statutory Compliance | Renovation of wet ash evacuation system from boiler to ash pump | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 1 | 70:30 | [6 empty] | 0.94444 | FY23: 0; FY24: 0; Estimated FY25: 0 | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 0.94444 | 0 | 0 | 0 | [13 empty] | 0.18114 | 0.18114 | 0 |  |  |  |  | 0 | [13 empty] | 0.8 | 28 | 0.8 |  |  | 0.8 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
29 | 4.7 | RInfra-G/DPR/BP11-16/DPR No 1.7 | Completed | Reliability Improvement/Statutory Compliance | Renovation of ash slurry cast basalt pipe line of ash slurry conveying system | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 2.5 | 70:30 | [6 empty] | 1.6604 | FY23: 0.75721; FY24: 0; Estimated FY25: 0 | 66.42% | 96.7% | 96.7% | 96.7% | 96.7% | 96.7% | 96.7% | 96.7% | 96.7% | 1.6604 | 0.75721 | 0 | 0 | [13 empty] | 0.62042 | 0.54046 | 0.079957 |  |  |  |  | 0 | [7 empty] | 0.13144 | 0.011127 | 0.010079 | 0.15265 |  |  | 0.2 | 267 | 0.2 |  |  | 0.2 |  |  |  | 0.2 |  |  | 0.2 |  |  |  | 0.3 |  |  | 0.3 |  |  |  | 0.3 |  |  | 0.3 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.2 | 0.3 | 0.3 | 0 | 0
30 | 4.8 | RInfra-G/DPR/BP11-16/DPR No 1.8 | Completed | Reliability Improvement/Statutory Compliance | Renovation of high pressure,low pressure rubber lined piping & valve fittings in ash handling system | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 2 | 70:30 | [6 empty] | 0.81274 | FY23: 0; FY24: 0; Estimated FY25: 0 | 40.64% | 40.64% | 40.64% | 40.64% | 40.64% | 40.64% | 40.64% | 40.64% | 40.64% | 0.81274 | 0 | 0 | 0 | [13 empty] | 0.15216 | 0 | 0 |  |  |  |  | 0 | [7 empty] | 0.18632 | 0.024561 | 0.013558 | 0.22444 |  |  | 0 | 172 | 0 |  |  | 0 |  |  |  | 0.6 |  |  | 0.6 |  |  |  | 0.5 |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.6 | 0.5 | 0.5 | 0 | 0
154 | 4.9 | RInfra-G/DPR/BP11-16/DPR No 1.9 | Completed | Reliability Improvement/Statutory Compliance | Renovation of bottom ash hoppers & its anticorrosive painting | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 1 | 70:30 | [6 empty] | 0.95096 | FY23: 0; FY24: 0; Estimated FY25: 0 | 95.1% | 95.1% | 95.1% | 95.1% | 95.1% | 95.1% | 95.1% | 95.1% | 95.1% | 0.95096 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [11 empty] | 0.15111 | 0.15111 | 0.69889 | 30 | 0.85 |  |  | 0.85 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
36 | 4.1 | RInfra-G/DPR/BP11-16/DPR No 1.10 | Completed | Reliability Improvement/Statutory Compliance | Renovation of ash bund bridge | MERC/Tech-IX/CAPEX/201202013/01549 | 2012-10-11 | 0.6 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0.15763 | 0.1649 | 0 |  |  |  |  | 0 | [13 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[72 empty] | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5 | RInfra-G/DPR/BP11-16//DPR No 2 |  |  | Renovation & Modernization Of Turbine and its auxiliaries | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 51.7 | 70:30 |  | FY 11-12 |  | FY 15-16 |  |  | 25.8822 | 2.1027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.05% | 54.15% | 54.15% | 54.15% | 54.15% | 54.15% | 54.15% | 54.15% | 54.15% | 25.8747 | 2.1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 6.0962 | 6.331 | 0 | 0 | 3.9809 | 0.16532 | 0 | 4.1462 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.065662 | 0.065662 | 0.53434 | 11 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.1 | RInfra-G/DPR/BP11-16/DPR No 2.1 | Surrender |  | Renovation of LP & Ip Rotor | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 8 | 70:30 |  | FY 11-12 | FY 11-12 | FY 15-16 | FY 20-21 | 1. Efficieny Improvement 2. Reliability Improvement | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.2 | RInfra-G/DPR/BP11-16/DPR No 2.2 | Completed | Efficiency Improvement | Renovation of Unit-1 HP turbine module | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 14.6 | 70:30 | [6 empty] | 11.8242 | FY23: 0; FY24: 0; Estimated FY25: 0 | 80.99% | 80.99% | 80.99% | 80.99% | 80.99% | 80.99% | 80.99% | 80.99% | 80.99% | 11.8242 | 0 | 0 | 0 | [13 empty] | 0.0295 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.3 | RInfra-G/DPR/BP11-16/DPR No 2.3 | Completed | Reliability Improvement | Renovation of turbine governing system & HP,IP control and stop valves | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 4 | 70:30 | [6 empty] | 3.62 | FY23: 2.05; FY24: 0; Estimated FY25: 0 | 90.5% | 142% | 142% | 142% | 142% | 142% | 142% | 142% | 142% | 3.62 | 2.06 | 0 | 0 | [13 empty] | 1.9738 | 2.238 | 0 |  | 1.6522 | 0.097497 |  | 1.7497 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.4 | RInfra-G/DPR/BP11-16/DPR No 2.4 | Completed | Reliability Improvement | Procurement of modified new design HP Bypass spray valves | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 1.35 | 70:30 | [6 empty] | 1.2676 | FY23: 0; FY24: 0; Estimated FY25: 0 | 93.89% | 93.89% | 93.89% | 93.89% | 93.89% | 93.89% | 93.89% | 93.89% | 93.89% | 1.2676 | 0 | 0 | 0 | [13 empty] | 0.64171 | 0.64171 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
17 | 5.5 | RInfra-G/DPR/BP11-16/DPR No 2.5 | Completed | Efficiency Improvement | Renovation of BFP cartridges | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 3 | 70:30 | [6 empty] | 2.9045 | FY23: 0; FY24: 0; Estimated FY25: 0 | 96.82% | 96.82% | 96.82% | 96.82% | 96.82% | 96.82% | 96.82% | 96.82% | 96.82% | 2.9045 | 0 | 0 | 0 | [13 empty] | 1.0158 | 1.0158 | 0 |  | 0.49954 | 0.025968 |  | 0.5255 | [11 empty] | 0.065662 | 0.065662 | 0.53434 | 11 | 0.6 |  |  | 0.6 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 5.6 | RInfra-G/DPR/BP11-16/DPR No 2.6 | Completed | Efficiency Improvement | Procurement of new BFP cartridge | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 5 | 70:30 | [6 empty] | 0.57271 | FY23: 0; FY24: 0; Estimated FY25: 0 | 11.45% | 11.45% | 11.45% | 11.45% | 11.45% | 11.45% | 11.45% | 11.45% | 11.45% | 0.57271 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.80509 | 0.041852 |  | 0.84695 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.7 | RInfra-G/DPR/BP11-16/DPR No 2.7 | Completed | Efficiency Improvement | Renovation of BFP hydraulic couplings | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 1 | 70:30 | [6 empty] | 1.024 | FY23: 0; FY24: 0; Estimated FY25: 0 | 102.4% | 102.4% | 102.4% | 102.4% | 102.4% | 102.4% | 102.4% | 102.4% | 102.4% | 1.024 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 1.024 | 0 |  | 1.024 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.8 | RInfra-G/DPR/BP11-16/DPR No 2.8 | Completed | Efficiency Improvement | Renovation of CEP cartridge | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 1 | 70:30 | [6 empty] | 0.12558 | FY23: 0.052678; FY24: 0; Estimated FY25: 0 | 11.81% | 17.83% | 17.83% | 17.83% | 17.83% | 17.83% | 17.83% | 17.83% | 17.83% | 0.11807 | 0.060186 | 0 | 0 | [13 empty] | 0.48042 | 0.48042 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.9 | RInfra-G/DPR/BP11-16/DPR No 2.9 | Completed | Reliability Improvement | Procurement & installation of condenser inlet valve | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 1.5 | 70:30 | [6 empty] | 1.3474 | FY23: 0; FY24: 0; Estimated FY25: 0 | 89.82% | 89.82% | 89.82% | 89.82% | 89.82% | 89.82% | 89.82% | 89.82% | 89.82% | 1.3474 | 0 | 0 | 0 | [13 empty] | 0.5453 | 0.5453 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.1 | RInfra-G/DPR/BP11-16/DPR No 2.10 | Completed | Reliability Improvement | Procurement of modified new design debris filter | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 8 | 70:30 | [6 empty] | 3.1962 | FY23: 0; FY24: 0; Estimated FY25: 0 | 39.95% | 39.95% | 39.95% | 39.95% | 39.95% | 39.95% | 39.95% | 39.95% | 39.95% | 3.1962 | 0 | 0 | 0 | [13 empty] | 1.4097 | 1.4097 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 5.11 | RInfra-G/DPR/BP11-16/DPR No 2.11 | Completed | Reliability Improvement | Installing modified design of COLTS system | MERC/Tech-IX/CAPEX/201202013/01905 | 2012-12-03 | 4.25 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[77 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 6 | RInfra-G/DPR/BP11-16//DPR No 3 |  |  | Renovation & Modernization Of Boiler and its auxiliaries | MERC/Tech-IX/CAPEX/201202013/02179 | 2012-12-27 | 22.9 | 70:30 |  | FY 12-13 |  | FY 15-16 |  |  | 8.4075 | 1.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.71% | 41.39% | 41.39% | 41.39% | 41.39% | 41.39% | 41.39% | 41.39% | 41.39% | 8.4067 | 1.0706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 1.2347 | 1.1291 | 0.1056 | 0 | 0.87663 | 0.02674 | 0 | 0.90337 | 0.020613 |  |  | 0 | 0 | 0.020613 | 0 | 2.0533 | 0.25806 | 0.0017645 | 2.3131 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 8.2 | 0 | 0 | 8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 0 | 0 | 0 | 0
| 6.1 | RInfra-G/DPR/BP11-16/DPR No 3.1 | Completed | Efficiency Improvement | Renovation & Modernisation of Flue gas path duct | MERC/Tech-IX/CAPEX/201202013/02179 | 2012-12-27 | 1.7 | 70:30 |  | FY 12-13 | FY 12-13 | FY 15-16 | FY 20-21 | 1. Efficieny Improvement 2. Reliability Improvement | 1.7236 | FY23: 0; FY24: 0; Estimated FY25: 0 | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 1.7236 | 0 | 0 | 0 | [13 empty] | 0.71107 | 0.71107 | 0 |  | 0.52615 | 0.0064606 |  | 0.53261 | [7 empty] | 0.48411 | 0.060844 | 0 | 0.54495 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
66 | 6.2 | RInfra-G/DPR/BP11-16/DPR No 3.2 | Completed | Reliability Improvement | Renovation of FD fan rotor | MERC/Tech-IX/CAPEX/201202013/02179 | 2012-12-27 | 1.2 | 70:30 | [6 empty] | 0.94945 | FY23: 0; FY24: 0; Estimated FY25: 0 | 79.12% | 79.12% | 79.12% | 79.12% | 79.12% | 79.12% | 79.12% | 79.12% | 79.12% | 0.94945 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [14 empty] | 60 | 0 |  |  | 0 |  |  | 1.2 | 1.2 |  |  | 1.2 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 1.2 | 0 | 0 | 0 | 0
67 | 6.3 | RInfra-G/DPR/BP11-16/DPR No 3.3 | Completed | Reliability Improvement | Renovation of PA fan rotor | MERC/Tech-IX/CAPEX/201202013/02179 | 2012-12-27 | 3 | 70:30 | [6 empty] | 2.0727 | FY23: 0; FY24: 0; Estimated FY25: 0 | 69.09% | 69.09% | 69.09% | 69.09% | 69.09% | 69.09% | 69.09% | 69.09% | 69.09% | 2.0727 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [14 empty] | 61 | 0 |  |  | 0 |  |  | 3 | 3 |  |  | 3 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 3 | 0 | 0 | 0 | 0
| 6.4 | RInfra-G/DPR/BP11-16/DPR No 3.4 | Completed | Reliability Improvement | Renovation & Modernisation of Milling system | MERC/Tech-IX/CAPEX/201202013/02179 | 2012-12-27 | 2 | 70:30 | [6 empty] | 2.3793 | FY23: 0; FY24: 0; Estimated FY25: 0 | 119% | 119% | 119% | 119% | 119% | 119% | 119% | 119% | 119% | 2.3793 | 0 | 0 | 0 | [13 empty] | 0.52365 | 0.41805 | 0.1056 |  | 0.35047 | 0.020279 |  | 0.37075 | 0.020613 |  |  |  |  | 0.020613 |  | 1.5692 | 0.19722 | 0.0017645 | 1.7682 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
68 | 6.5 | RInfra-G/DPR/BP11-16/DPR No 3.5 | Completed | Reliability Improvement | Renovatiion & Modernisation of Girth gear | MERC/Tech-IX/CAPEX/201202013/02179 | 2012-12-27 | 15 | 70:30 | [6 empty] | 1.2824 | FY23: 1.0699; FY24: 0; Estimated FY25: 0 | 8.544% | 15.68% | 15.68% | 15.68% | 15.68% | 15.68% | 15.68% | 15.68% | 15.68% | 1.2817 | 1.0706 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [14 empty] | 62 | 0 |  |  | 0 |  |  | 4 | 4 |  |  | 4 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 4 | 0 | 0 | 0 | 0
[77 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 7 | RInfra-G/DPR/BP11-16//DPR No 4 |  |  | Renovation & Modernization Of Offsite Plant auxiliaries | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 15.49 | 70:30 |  | FY 11-12 |  | FY 15-16 |  |  | 9.6476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.28% | 62.28% | 62.28% | 62.28% | 62.28% | 62.28% | 62.28% | 62.28% | 62.28% | 9.6476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 4.1621 | 4.1024 | 0.05973 | 0 | 3.4966 | 0.0044843 | 0 | 3.5011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 12 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.1 | RInfra-G/DPR/BP11-16/DPR No 4.1 | Completed | Reliability Improvement | Renovation of Auxiliary cooling water pumps & allied systems | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 1.75 | 70:30 |  | FY 11-12 | FY 11-12 | FY 15-16 | FY 20-21 | 1. Reliability Improvement | 1.2784 | FY23: 0; FY24: 0; Estimated FY25: 0 | 73.05% | 73.05% | 73.05% | 73.05% | 73.05% | 73.05% | 73.05% | 73.05% | 73.05% | 1.2784 | 0 | 0 | 0 | [13 empty] | 0.10715 | 0.047424 | 0.05973 |  | 0.63866 | 0.0044843 |  | 0.64314 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 7.2 | RInfra-G/DPR/BP11-16/DPR No 4.2 | Completed | Reliability Improvement | Procurement of PHE plates | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 4.8 | 70:30 | [6 empty] | 0.82773 | FY23: 0; FY24: 0; Estimated FY25: 0 | 17.24% | 17.24% | 17.24% | 17.24% | 17.24% | 17.24% | 17.24% | 17.24% | 17.24% | 0.82773 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.82773 | 0 |  | 0.82773 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 7.3 | RInfra-G/DPR/BP11-16/DPR No 4.3 | Completed | Reliability Improvement | Procurement and installation of New Cw pump outlet valve | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 3 | 70:30 | [6 empty] | 3.2054 | FY23: 0; FY24: 0; Estimated FY25: 0 | 106.8% | 106.8% | 106.8% | 106.8% | 106.8% | 106.8% | 106.8% | 106.8% | 106.8% | 3.2054 | 0 | 0 | 0 | [13 empty] | 1.99 | 1.99 | 0 |  | 1.2154 | 0 |  | 1.2154 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 7.4 | RInfra-G/DPR/BP11-16/DPR No 4.4 | Completed | Reliability Improvement | Renovating of CW pumps | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 0.9 | 70:30 | [6 empty] | 0.99587 | FY23: 0; FY24: 0; Estimated FY25: 0 | 110.7% | 110.7% | 110.7% | 110.7% | 110.7% | 110.7% | 110.7% | 110.7% | 110.7% | 0.99587 | 0 | 0 | 0 | [13 empty] | 0.99587 | 0.99587 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
18 | 7.5 | RInfra-G/DPR/BP11-16/DPR No 4.5 | Completed | Reliability Improvement | Renovating of TWS | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 5.04 | 70:30 | [6 empty] | 3.3401 | FY23: 0; FY24: 0; Estimated FY25: 0 | 66.27% | 66.27% | 66.27% | 66.27% | 66.27% | 66.27% | 66.27% | 66.27% | 66.27% | 3.3401 | 0 | 0 | 0 | [13 empty] | 1.0691 | 1.0691 | 0 |  | 0.81479 | 0 |  | 0.81479 | [13 empty] | 0.5 | 12 | 0.5 |  |  | 0.5 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 8 | RInfra-G/DPR/BP11-16//DPR No 5 |  |  | Bundled DPR of Non-DPR schemes of DTPS for Business Plan Period | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 19.79 | 70:30 |  | FY 11-12 |  | FY 15-16 |  |  | 7.1471 | 1.1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.11% | 42.17% | 42.17% | 42.17% | 42.17% | 42.17% | 42.17% | 42.17% | 42.17% | 7.1471 | 1.1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 3.8057 | 3.8125 | 0 | 0 | 2.1136 | 0 | 0 | 2.1136 | 0.012435 |  |  | 0 | 0 | 0.012435 | 0 | 0.02006 | 0 | 0 | 0.02006 | 0.012435 | 0.012435 | 0.25 | 69 | 0.26243 | 0 | 0 | 0.26243 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
| 8.1 | RInfra-G/DPR/BP11-16/DPR No 5.1 | Completed | Reliability Improvement/Statutory Requirement | Procurement of oxidation Cartridge assembly | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 1.8 | 70:30 |  | FY 11-12 | FY 11-12 | FY 15-16 | FY 19-20 | 1. Statutory Compliance 2. Reliability Improvement 3. Safety & Security enhancement | 0.42847 | FY23: 0.50861; FY24: 0; Estimated FY25: 0 | 23.8% | 52.06% | 52.06% | 52.06% | 52.06% | 52.06% | 52.06% | 52.06% | 52.06% | 0.42847 | 0.50861 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.42847 | 0 |  | 0.42847 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.2 | RInfra-G/DPR/BP11-16/DPR No 5.2 | Completed | Reliability Improvement/Statutory Requirement | Renovation of FGD sea water pumps & installation of filtration Unit | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 3 | 70:30 | [6 empty] | 3.0067 | FY23: 0; FY24: 0; Estimated FY25: 0 | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 3.0067 | 0 | 0 | 0 | [13 empty] | 1.7896 | 1.7896 | 0 |  | 1.2171 | 0 |  | 1.2171 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.3 | RInfra-G/DPR/BP11-16/DPR No 5.3 | Completed | Reliability Improvement/Statutory Requirement | Renovation of FGD sea water piping | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.4 | RInfra-G/DPR/BP11-16/DPR No 5.4 | Completed | Reliability Improvement/Statutory Requirement | Renovation & Development of DTPS stores | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 3.67 | 70:30 | [6 empty] | 0.93059 | FY23: 0.62136; FY24: 0; Estimated FY25: 0 | 25.36% | 42.29% | 42.29% | 42.29% | 42.29% | 42.29% | 42.29% | 42.29% | 42.29% | 0.93059 | 0.62136 | 0 | 0 | [13 empty] | 0.11049 | 0.11049 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
37 | 8.5 | RInfra-G/DPR/BP11-16/DPR No 5.5 | Completed | Reliability Improvement/Statutory Requirement | Procurement of Material Handling equipments | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 1.99 | 70:30 | [6 empty] | 0.4894 | FY23: 0; FY24: 0; Estimated FY25: 0 | 24.59% | 24.59% | 24.59% | 24.59% | 24.59% | 24.59% | 24.59% | 24.59% | 24.59% | 0.4894 | 0 | 0 | 0 | [13 empty] | 0.4894 | 0.4894 | 0 |  |  |  |  | 0 | [13 empty] | 0.25 | 31 | 0.25 |  |  | 0.25 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 8.6 | RInfra-G/DPR/BP11-16/DPR No 5.6 | Completed | Reliability Improvement/Statutory Requirement | Online Display & Connectivity to MPCB website of envirnmental parameters | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.1 | 70:30 | [6 empty] | 0.099087 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.09% | 99.09% | 99.09% | 99.09% | 99.09% | 99.09% | 99.09% | 99.09% | 99.09% | 0.099087 | 0 | 0 | 0 | [13 empty] | 0.099087 | 0.10586 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.7 | RInfra-G/DPR/BP11-16/DPR No 5.7 | Completed | Reliability Improvement/Statutory Requirement | Purchase of New SO2,NOX & Ozone analysere for AAQM | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.85 | 70:30 | [6 empty] | 0.72562 | FY23: 0; FY24: 0; Estimated FY25: 0 | 85.37% | 85.37% | 85.37% | 85.37% | 85.37% | 85.37% | 85.37% | 85.37% | 85.37% | 0.72562 | 0 | 0 | 0 | [13 empty] | 0.53064 | 0.53064 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.8 | RInfra-G/DPR/BP11-16/DPR No 5.8 | Completed | Reliability Improvement/Statutory Requirement | Up-gradation of AAQM analysers to measure particulate matter | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.5 | 70:30 | [6 empty] | 0.18563 | FY23: 0; FY24: 0; Estimated FY25: 0 | 37.12% | 37.12% | 37.12% | 37.12% | 37.12% | 37.12% | 37.12% | 37.12% | 37.12% | 0.18563 | 0 | 0 | 0 | [13 empty] | 0.18563 | 0.18563 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.9 | RInfra-G/DPR/BP11-16/DPR No 5.9 | Completed | Reliability Improvement/Statutory Requirement | Purchase of New mobile Van and AAQM analysers in it | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
44 | 8.1 | RInfra-G/DPR/BP11-16/DPR No 5.10 | Completed | Reliability Improvement/Statutory Requirement | Renovation & Modernization of fire fighting system | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.88 | 70:30 | [6 empty] | 0.63427 | FY23: 0; FY24: 0; Estimated FY25: 0 | 72.08% | 72.08% | 72.08% | 72.08% | 72.08% | 72.08% | 72.08% | 72.08% | 72.08% | 0.63427 | 0 | 0 | 0 | [13 empty] | 0.51424 | 0.51424 | 0 |  |  |  |  | 0 | [14 empty] | 38 | 0 |  |  | 0 |  |  | 0.5 | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0 | 0
| 8.11 | RInfra-G/DPR/BP11-16/DPR No 5.11 | Completed | Reliability Improvement/Statutory Requirement | Procurement & installation of RADAR and other security Equipments | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.5 | 70:30 | [6 empty] | 0.17931 | FY23: 0.069192; FY24: 0; Estimated FY25: 0 | 35.86% | 49.7% | 49.7% | 49.7% | 49.7% | 49.7% | 49.7% | 49.7% | 49.7% | 0.17931 | 0.069192 | 0 | 0 | [13 empty] | 0.086645 | 0.086645 | 0 |  |  |  |  | 0 | 0.012435 |  |  |  |  | 0.012435 |  | 0.02006 | 0 | 0 | 0.02006 | 0.012435 | 0.012435 | 0 |  | 0.012435 |  |  | 0.012435 | 0 |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.12 | RInfra-G/DPR/BP11-16/DPR No 5.12 | Completed | Reliability Improvement/Statutory Requirement | Renovation & Upgradation of PLC Systems & Networking for Reliability Improvement | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.5 | 70:30 | [6 empty] | 0.46802 | FY23: 0; FY24: 0; Estimated FY25: 0 | 93.6% | 93.6% | 93.6% | 93.6% | 93.6% | 93.6% | 93.6% | 93.6% | 93.6% | 0.46802 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.46802 | 0 |  | 0.46802 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 8.13 | RInfra-G/DPR/BP11-16/DPR No 5.13 | Completed | Reliability Improvement/Statutory Requirement | Renovation & Upgradation of weighing System for availability improvement | MERC/Tech-IX/CAPEX/20122013/00075 | 2013-04-05 | 0.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[77 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 9 | RInfra-G/DPR/BP11-16//DPR No 6 | Completed | Reliability Improvement | Procurement of Generator Rotor | MERC/CAPEX/201202013/01166 | 2012-08-29 | 29 | 70:30 |  | FY 12-13 |  | FY 12-13 |  | Reliability Improvement | 24.2793 | [8 empty] | 83.72% | 83.72% | 83.72% | 83.72% | 83.72% | 83.72% | 83.72% | 83.72% | 83.72% | 24.2793 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | #REF!
| 10 | RInfra-G/DPR/BP11-16//DPR No 7 | Completed | Reliability Improvement | Procurement of Generator Transformer | MERC/CAPEX/201202013/01165 | 2012-08-29 | 16 | 70:30 |  | FY 12-13 |  | FY 12-13 |  | Reliability Improvement | 9.4237 | [8 empty] | 58.9% | 58.9% | 58.9% | 58.9% | 58.9% | 58.9% | 58.9% | 58.9% | 58.9% | 9.4237 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | #REF!
| 11 | RInfra-G/DPR/BP11-16//DPR No 8 |  |  | Bundled DPR for Non-DPR Capex Schemes for Energy Conservation in Main Plant Auxiliaries and BOP | MERC/Tech-IX/CAPEX/20122013/02607 | 2013-02-11 | 11.6 | 70:30 |  | FY 12-13 |  | FY 15-16 |  |  | 3.6694 | 0.13597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.63% | 32.8% | 32.8% | 32.8% | 32.8% | 32.8% | 32.8% | 32.8% | 32.8% | 3.6694 | 0.13597 | 0 | 0 | [13 empty] | 1.1361 | 1.1361 | 0 | 0 | 0.48066 | 0.0039093 | 0 | 0.48457 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032061 | 0.032061 | 0 | 211 | 0.032061 | 0 | 0 | 0.032061 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 0 | 0
| 11.1 | RInfra-G/DPR/BP11-16/DPR No 8.1 | Completed | Reliability Improvement | Renovation & Modernization of Flluid coupling with magna couplings in CHP & AHP Equipments | MERC/Tech-IX/CAPEX/20122013/02607 | 2013-02-11 | 1.5 | 70:30 |  | FY 12-13 | FY 12-13 | FY 15-16 | FY 20-21 | 1. Energy Conservation | 0.14732 | FY23: 0; FY24: 0; Estimated FY25: 0 | 9.821% | 9.821% | 9.821% | 9.821% | 9.821% | 9.821% | 9.821% | 9.821% | 9.821% | 0.14732 | 0 | 0 | 0 | [13 empty] | 0.14732 | 0.14732 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
23 | 11.2 | RInfra-G/DPR/BP11-16/DPR No 8.2 | Completed | Reliability Improvement | Installation of VFD in ID fans | MERC/Tech-IX/CAPEX/20122013/02607 | 2013-02-11 | 5.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | [12 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
69 | 11.3 | RInfra-G/DPR/BP11-16/DPR No 8.3 | Completed | Reliability Improvement | Renovation of lighting system in plant And CHP tunnel area | MERC/Tech-IX/CAPEX/20122013/02607 | 2013-02-11 | 3.6 | 70:30 | [6 empty] | 3.2483 | FY23: 0.13597; FY24: 0; Estimated FY25: 0 | 90.23% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 94.01% | 3.2483 | 0.13597 | 0 | 0 | [13 empty] | 0.78964 | 0.78964 | 0 |  | 0.48066 | 0.0039093 |  | 0.48457 | [11 empty] | 0.032061 | 0.032061 | 0 | 211 | 0.032061 |  |  | 0.032061 | 0 |  | 0.5 | 0.5 |  |  | 0.5 |  |  |  | 1 |  |  | 1 |  |  |  | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.5 | 1 | 0.5 | 0 | 0
137 | 11.4 | RInfra-G/DPR/BP11-16/DPR No 8.4 | Completed | Reliability Improvement | Advanced Energy monitoring system by installation of Energy Meters | MERC/Tech-IX/CAPEX/20122013/02607 | 2013-02-11 | 1 | 70:30 | [6 empty] | 0.27372 | FY23: 0; FY24: 0; Estimated FY25: 0 | 27.37% | 27.37% | 27.37% | 27.37% | 27.37% | 27.37% | 27.37% | 27.37% | 27.37% | 0.27372 | 0 | 0 | 0 | [13 empty] | 0.19919 | 0.19919 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[77 empty] | 0 | [6 empty] | 0
| 12 | RInfra-G/DPR/BP11-16//DPR No 9 |  |  | Strengthening of Electrical System at DTPS | MERC/CAPEX/201202013/01539 | 2012-10-11 | 24.4 | 70:30 |  | FY 12-13 |  | FY 15-16 |  |  | 12.5299 | 0.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.33% | 53.97% | 53.97% | 53.97% | 53.97% | 53.97% | 53.97% | 53.97% | 53.97% | 12.5251 | 0.64417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 5.679 | 4.7905 | 0.9171 | 0 | 2.7857 | 0.080711 | 0 | 2.8664 | 0 |  |  | 0 | 0 | 0 | 0 | 0.032783 | 0 | 0 | 0.032783 | 0.0084604 | 0.0084604 | 0.87154 | 1096 | 0.88 | 0 | 0 | 0.88 | 0 | 0 | 0.5 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0.65 | 0 | 0 | 0.65 | 0 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.65 | 1.4 | 0 | 0
| 12.1 | RInfra-G/DPR/BP11-16/DPR No 9.1 | Completed | Reliability Improvement | Renovation & Modernization of AVR system | MERC/CAPEX/201202013/01539 | 2012-10-11 | 2 | 70:30 |  | FY 12-13 | FY 12-13 | FY 15-16 | FY 20-21 | 1. Reliability Improvement | 1.6635 | FY23: 0; FY24: 0; Estimated FY25: 0 | 83.17% | 83.17% | 83.17% | 83.17% | 83.17% | 83.17% | 83.17% | 83.17% | 83.17% | 1.6635 | 0 | 0 | 0 | [13 empty] | 1.6605 | 1.6653 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 12.2 | RInfra-G/DPR/BP11-16/DPR No 9.2 | Completed | Reliability Improvement | Renovation of Generator & Generator transformer Flexibles | MERC/CAPEX/201202013/01539 | 2012-10-11 | 1.2 | 70:30 | [6 empty] | 0.71186 | FY23: 0; FY24: 0; Estimated FY25: 0 | 59.32% | 59.32% | 59.32% | 59.32% | 59.32% | 59.32% | 59.32% | 59.32% | 59.32% | 0.71186 | 0 | 0 | 0 | [13 empty] | 0.14228 | 0.14228 | 0 |  | 0.24292 | 0 |  | 0.24292 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 12.3 | RInfra-G/DPR/BP11-16/DPR No 9.3 | Completed | Reliability Improvement | Procurement and installation of power pack for uninterrupted power supply for Generator sea oil pump system | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.2 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
71 | 12.4 | RInfra-G/DPR/BP11-16/DPR No 9.4 | Completed | Reliability Improvement | Renovation & Modernisation of protection system for Generator & associated Equipments | MERC/CAPEX/201202013/01539 | 2012-10-11 | 2 | 70:30 | [6 empty] | 1.5539 | FY23: 0; FY24: 0; Estimated FY25: 0 | 77.7% | 77.7% | 77.7% | 77.7% | 77.7% | 77.7% | 77.7% | 77.7% | 77.7% | 1.5539 | 0 | 0 | 0 | [13 empty] | 1.523 | 0.6309 | 0.89212 |  | 0.92304 | 0.066977 |  | 0.99002 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
138 | 12.5 | RInfra-G/DPR/BP11-16/DPR No 9.5 | Completed | Reliability Improvement | Online condition monitoring of Electrical Equipments | MERC/CAPEX/201202013/01539 | 2012-10-11 | 3 | 70:30 | [6 empty] | 0.51541 | FY23: 0; FY24: 0; Estimated FY25: 0 | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 17.18% | 0.51541 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [14 empty] | 197 | 0 |  |  | 0 |  |  | 0.5 | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  | 0 |  |  |  | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.5 | 0 | 0.5 | 0 | 0
72 | 12.6 | RInfra-G/DPR/BP11-16/DPR No 9.6 | Completed | Reliability Improvement | Renovation of 6.6kV HT swtchgear | MERC/CAPEX/201202013/01539 | 2012-10-11 | 5 | 70:30 | [6 empty] | 1.9304 | FY23: 0; FY24: 0; Estimated FY25: 0 | 38.61% | 38.61% | 38.61% | 38.61% | 38.61% | 38.61% | 38.61% | 38.61% | 38.61% | 1.9304 | 0 | 0 | 0 | [13 empty] | 0.19224 | 0.19224 | 0 |  | 0.87105 | 0 |  | 0.87105 | [13 empty] | 0.4 | 66 | 0.4 |  |  | 0.4 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
139 | 12.7 | RInfra-G/DPR/BP11-16/DPR No 9.7 | Completed | Reliability Improvement | Reliability improvement by replacing SF6 circuit breakers with vacuum contactors | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.75 | 70:30 | [6 empty] | 0.31189 | FY23: 0.31174; FY24: 0; Estimated FY25: 0 | 41.3% | 83.15% | 83.15% | 83.15% | 83.15% | 83.15% | 83.15% | 83.15% | 83.15% | 0.30978 | 0.31385 | 0 | 0 | [13 empty] | 0.30978 | 0.30978 | 0 |  |  |  |  | 0 | [14 empty] | 133 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0.15 |  |  | 0.15 |  |  |  | 0.15 |  |  | 0.15 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0.15 | 0.15 | 0 | 0
24 | 12.8 | RInfra-G/DPR/BP11-16/DPR No 9.8 | Completed | Reliability Improvement | Renovation & Modernization of fast Bus Transfer System | MERC/CAPEX/201202013/01539 | 2012-10-11 | 1 | 70:30 | [6 empty] | 0.65471 | FY23: 0; FY24: 0; Estimated FY25: 0 | 65.47% | 65.47% | 65.47% | 65.47% | 65.47% | 65.47% | 65.47% | 65.47% | 65.47% | 0.65471 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [14 empty] | 85 | 0 |  |  | 0 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 | 0
73 | 12.9 | RInfra-G/DPR/BP11-16/DPR No 9.9 | Completed | Reliability Improvement | Renovation & Modernisation of LT switchgear System | MERC/CAPEX/201202013/01539 | 2012-10-11 | 1.25 | 70:30 | [6 empty] | 0.78149 | FY23: 0.32766; FY24: 0; Estimated FY25: 0 | 62.31% | 88.73% | 88.73% | 88.73% | 88.73% | 88.73% | 88.73% | 88.73% | 88.73% | 0.77883 | 0.33032 | 0 | 0 | [13 empty] | 0.57725 | 0.57725 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 12.1 | RInfra-G/DPR/BP11-16/DPR No 9.10 | Completed | Reliability Improvement | Renovation & Modernisation of 220KV switchyard Equipments | MERC/CAPEX/201202013/01539 | 2012-10-11 | 2.25 | 70:30 | [6 empty] | 1.4448 | FY23: 0; FY24: 0; Estimated FY25: 0 | 64.21% | 64.21% | 64.21% | 64.21% | 64.21% | 64.21% | 64.21% | 64.21% | 64.21% | 1.4448 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.21899 | 0 |  | 0.21899 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 12.11 | RInfra-G/DPR/BP11-16/DPR No 9.11 | Completed | Reliability Improvement | Renovation & Modernisation of 33KV Switchyard equi8pments | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 12.12 | RInfra-G/DPR/BP11-16/DPR No 9.12 | Completed | Reliability Improvement | Up-gradation of ESP Rapper Controllersfor ESP | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.6 | 70:30 | [6 empty] | 0.59475 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.12% | 99.12% | 99.12% | 99.12% | 99.12% | 99.12% | 99.12% | 99.12% | 99.12% | 0.59475 | 0 | 0 | 0 | [13 empty] | 0.36288 | 0.36288 | 0 |  | 0.23187 | 0 |  | 0.23187 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 12.13 | RInfra-G/DPR/BP11-16/DPR No 9.13 | Completed | Reliability Improvement | Provision of dedicated Express power supply feeder for Kawdas pump house | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.25 | 70:30 | [6 empty] | 0.23584 | FY23: 0; FY24: 0; Estimated FY25: 0 | 94.34% | 94.34% | 94.34% | 94.34% | 94.34% | 94.34% | 94.34% | 94.34% | 94.34% | 0.23584 | 0 | 0 | 0 | [13 empty] | 0.23584 | 0.23584 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
140 | 12.14 | RInfra-G/DPR/BP11-16/DPR No 9.14 | Completed | Reliability Improvement | Renovation & Modernisation of transformer radiators | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.5 | 70:30 | [6 empty] | 0.32761 | FY23: 0; FY24: 0; Estimated FY25: 0 | 65.52% | 65.52% | 65.52% | 65.52% | 65.52% | 65.52% | 65.52% | 65.52% | 65.52% | 0.32761 | 0 | 0 | 0 | [13 empty] | 0.054968 | 0.054968 | 0 |  | 0.13961 | 0.010481 |  | 0.15009 | [14 empty] | 134 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0.5 | 0 | 0
74 | 12.15 | RInfra-G/DPR/BP11-16/DPR No 9.15 | Completed | Reliability Improvement | Procurement of battery for Emergency DC lighting sysytem | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 | [6 empty] | 0 | [16 empty] | 0 | [6 empty] | 0
141 | 12.16 | RInfra-G/DPR/BP11-16/DPR No 9.16 | Completed | Reliability Improvement | Renovation & Modernisation of hoists in main plant area | MERC/CAPEX/201202013/01539 | 2012-10-11 | 0.4 | 70:30 | [6 empty] | 0.18938 | FY23: 0; FY24: 0; Estimated FY25: 0 | 47.34% | 47.34% | 47.34% | 47.34% | 47.34% | 47.34% | 47.34% | 47.34% | 47.34% | 0.18938 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.07226 | 0.0013776 |  | 0.073638 | [14 empty] | 135 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  |  | 0.1 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0.1 | 0.1 | 0 | 0
25 | 12.17 | RInfra-G/DPR/BP11-16/DPR No 9.17 | Completed | Reliability Improvement | Strengthening of cable tray & supporting structure | MERC/CAPEX/201202013/01539 | 2012-10-11 | 1 | 70:30 | [6 empty] | 0.91636 | FY23: 0; FY24: 0; Estimated FY25: 0 | 91.64% | 91.64% | 91.64% | 91.64% | 91.64% | 91.64% | 91.64% | 91.64% | 91.64% | 0.91636 | 0 | 0 | 0 | [13 empty] | 0.62027 | 0.6191 | 0.024976 |  | 0.085946 | 0.0018751 |  | 0.087821 | [7 empty] | 0.032783 | 0 | 0 | 0.032783 | 0.0084604 | 0.0084604 | 0.22154 | 87 | 0.23 |  |  | 0.23 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
56 | 12.18 | RInfra-G/DPR/BP11-16/DPR No 9.18 | Completed | Reliability Improvement | Renovation & Modernization of Protection system for LT Switchgear | MERC/CAPEX/201202013/01539 | 2012-10-11 | 2 | 70:30 | [6 empty] | 0.69794 | FY23: 0; FY24: 0; Estimated FY25: 0 | 34.9% | 34.9% | 34.9% | 34.9% | 34.9% | 34.9% | 34.9% | 34.9% | 34.9% | 0.69794 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [13 empty] | 0.25 | 259 | 0.25 |  |  | 0.25 |  |  |  | 0 |  |  | 0 |  |  |  | 0.4 |  |  | 0.4 |  |  |  | 0.15 |  |  | 0.15 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0.4 | 0.15 | 0 | 0
79 | [76 empty] | 0 | [6 empty] | 0
143 | 13 | RInfra-G/DPR/BP11-16/DPR No 10 |  |  | Renovation & Modernization of Control & Instrumentation System of Main Plant | MERC/Tech-IX/CAPEX/201202013/01798 | 2012-11-12 | 60 | 70:30 |  | FY 12-13 |  | FY 15-16 |  |  | 13.2695 | 5.8307 | 1.2302 | 0 | 0 | 0 | 0 | 0 | 0 | 22.01% | 24.72% | 33.88% | 33.88% | 33.88% | 33.88% | 33.88% | 33.88% | 33.88% | 13.2049 | 1.6274 | 5.4982 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 9.0988 | 9.0988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.37 | 0 | 0 | 6.37 | 0 | 0 | 0 | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 6.37 | 1.49 | 0 | 40
91 | 13.1 | RInfra-G/DPR/BP11-16/DPR No 10.1 | Completed | Reliability Improvement | Modernization and up-gradation of Electronic cards of distributed Digital control(DDC) system of Unit-1 | MERC/Tech-IX/CAPEX/201202013/01798 | 2012-11-12 | 5 | 70:30 |  | FY 12-13 | FY 12-13 | FY 15-16 | FY 20-21 | 1. Reliability Improvement | 4.8664 | FY23: 0.0021018; FY24: 0; Estimated FY25: 0 | 97.33% | 97.37% | 97.37% | 97.37% | 97.37% | 97.37% | 97.37% | 97.37% | 97.37% | 4.8664 | 0.0021018 | 0 | 0 | [13 empty] | 2.9593 | 2.9593 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
125 | 13.2 | RInfra-G/DPR/BP11-16/DPR No 10.2 | Completed | Reliability Improvement | Renovation & Modernization of complete DDC system for reliability improvement of Unit-2 | MERC/Tech-IX/CAPEX/201202013/01798 | 2012-11-12 | 50 | 70:30 | [6 empty] | 8.2116 | FY23: 1.6253; FY24: 0.71315; Estimated FY25: 0 | 16.42% | 19.67% | 21.1% | 21.1% | 21.1% | 21.1% | 21.1% | 21.1% | 21.1% | 8.2116 | 1.6253 | 0.71315 | 0 | [13 empty] | 6.0127 | 6.0127 | 0 |  |  |  |  | 0 | [14 empty] | 377 | 1 |  |  | 1 |  |  | 0 | 0 |  |  | 0 |  |  |  | 1.5 |  |  | 1.5 |  |  |  | 1.49 |  |  | 1.49 |  |  |  | 0 |  |  | 0 |  |  |  | 40 |  |  |  | 40 | 0 | 1.5 | 1.49 | 0 | 40
179 | 13.3 | RInfra-G/DPR/BP11-16/DPR No 10.3 | Completed | Reliability Improvement | Upgradation of governing system,HPBP,LPBP and turbovisory in Unit-2 | MERC/Tech-IX/CAPEX/201202013/01798 | 2012-11-12 | 5 | 70:30 | [6 empty] | 0.19156 | FY23: 4.2032; FY24: 0.51707; Estimated FY25: 0 | 2.537% | 2.537% | 98.24% | 98.24% | 98.24% | 98.24% | 98.24% | 98.24% | 98.24% | 0.12686 | 0 | 4.785 | 0 | [13 empty] | 0.12686 | 0.12686 | 0 |  |  |  |  | 0 | [14 empty] | 86 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  |  | 4.87 |  |  | 4.87 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 4.87 | 0 | 0 | 0
[77 empty] | 0 | [6 empty] | 0
92 | 14 | RInfra-G/DPR/BP11-16/DPR No 11 |  |  | Renovation & Modernization Of Coal Handling System | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 23.05 | 70:30 |  | FY 11-12 |  | FY 15-16 |  |  | 18.3044 | 0.79915 | 1.4609 | 0 | 0 | 0 | 0 | 0 | 0 | 79.41% | 82.88% | 89.22% | 89.22% | 89.22% | 89.22% | 89.22% | 89.22% | 89.22% | 18.3044 | 0.79915 | 1.4609 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8.7254 | 8.3647 | 0.11023 | 0 | 1.2438 | 0.036034 | 0 | 1.2798 | 0.36455 |  |  | 0 | 0 | 0.36455 | 0 | 1.3201 | 0.14517 | 0.039722 | 1.505 | 0.015353 | 0.015353 | 1.0941 | 150 | 1.1095 | 0 | 0 | 1.1095 | 0 | 0 | 0.5 | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0
| 14.1 | RInfra-G/DPR/BP11-16/DPR No 11.1 | Completed | Reliability Improvement | Renovation of crushers for availability and reliability improvement | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 4 | 70:30 |  | FY 11-12 | FY 11-12 | FY 15-16 | FY 20-21 | 1. Relibility Improvement | 0 | FY23: 0.79915; FY24: 1.4609; Estimated FY25: 0 | 0% | 19.98% | 56.5% | 56.5% | 56.5% | 56.5% | 56.5% | 56.5% | 56.5% | 0 | 0.79915 | 1.4609 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 14.2 | RInfra-G/DPR/BP11-16/DPR No 11.2 | Completed | Reliability Improvement | Renovation of stacker reclaimer for reliability improvement | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 2.8 | 70:30 | [6 empty] | 2.7682 | FY23: 0; FY24: 0; Estimated FY25: 0 | 98.86% | 98.86% | 98.86% | 98.86% | 98.86% | 98.86% | 98.86% | 98.86% | 98.86% | 2.7682 | 0 | 0 | 0 | [13 empty] | 1.8284 | 1.8284 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
20 | 14.3 | RInfra-G/DPR/BP11-16/DPR No 11.3 | Completed | Reliability Improvement | Renovation of belt conveyers alongwith structures | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 3.1 | 70:30 | [6 empty] | 3.8353 | FY23: 0; FY24: 0; Estimated FY25: 0 | 123.7% | 123.7% | 123.7% | 123.7% | 123.7% | 123.7% | 123.7% | 123.7% | 123.7% | 3.8353 | 0 | 0 | 0 | [13 empty] | 1.557 | 1.3191 | 0.11023 |  | 0.28607 | 0.0082754 |  | 0.29434 | 0.36455 |  |  |  |  | 0.36455 |  | 0.43676 | 0.051484 | 0.039722 | 0.52796 | 0.015353 | 0.015353 | 0 | 14 | 0.015353 |  |  | 0.015353 | 0 |  | 0.5 | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0 | 0
13 | 14.4 | RInfra-G/DPR/BP11-16/DPR No 11.4 | Completed | Reliability Improvement | Renovation of structure in CHP | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 2.65 | 70:30 | [6 empty] | 2.6407 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.65% | 99.65% | 99.65% | 99.65% | 99.65% | 99.65% | 99.65% | 99.65% | 99.65% | 2.6407 | 0 | 0 | 0 | [13 empty] | 1.2634 | 1.3361 | 0 |  | 0.32057 | 0 |  | 0.32057 | [7 empty] | 0.88334 | 0.093683 | 0 | 0.97702 |  |  | 1.0941 | 22 | 1.0941 |  |  | 1.0941 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 14.5 | RInfra-G/DPR/BP11-16/DPR No 11.5 | Completed | Reliability Improvement | Renovatiion of coal yards | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 5 | 70:30 | [6 empty] | 4.6274 | FY23: 0; FY24: 0; Estimated FY25: 0 | 92.55% | 92.55% | 92.55% | 92.55% | 92.55% | 92.55% | 92.55% | 92.55% | 92.55% | 4.6274 | 0 | 0 | 0 | [13 empty] | 0.84654 | 0.84654 | 0 |  | 0.63714 | 0.027759 |  | 0.6649 | [14 empty] | 33 | 0 |  |  | 0 |  |  |  | 0.7 |  |  | 0.7 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.7 | 0 | 0 | 0 | 0
39 | 14.6 | RInfra-G/DPR/BP11-16/DPR No 11.6 | Completed | Reliability Improvement | Renovation of Dozers | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 2 | 70:30 | [6 empty] | 2.0712 | FY23: 0; FY24: 0; Estimated FY25: 0 | 103.6% | 103.6% | 103.6% | 103.6% | 103.6% | 103.6% | 103.6% | 103.6% | 103.6% | 2.0712 | 0 | 0 | 0 | [13 empty] | 0.94712 | 0.75159 | 0 |  |  |  |  | 0 | [13 empty] | 0 | 81 | 0 |  |  | 0 |  |  |  | 0.6 |  |  | 0.6 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.6 | 0 | 0 | 0 | 0
87 | 14.7 | RInfra-G/DPR/BP11-16/DPR No 11.7 | Completed | Reliability Improvement | Procurement of eathmoving equipments | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 2 | 70:30 | [6 empty] | 2.3616 | FY23: 0; FY24: 0; Estimated FY25: 0 | 118.1% | 118.1% | 118.1% | 118.1% | 118.1% | 118.1% | 118.1% | 118.1% | 118.1% | 2.3616 | 0 | 0 | 0 | [13 empty] | 2.2829 | 2.2829 | 0 |  |  |  |  | 0 | [18 empty] | 0 | [6 empty] | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 14.8 | RInfra-G/DPR/BP11-16/DPR No 11.8 | Completed | Reliability Improvement | Installation of tube conveyor from primary crusher houses to coal yard-1 | MERC/Tech-IX/CAPEX/201202013/02180 | 2012-12-27 | 1.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | [12 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[64 empty] | 0 | [12 empty] | 0 | [6 empty] | 0
| 15 | RInfra-G/DPR/BP11-16/DPR No 12 | Surrender |  | Electro Clorination System | MERC/Tech-IX/CAPEX/201202013/01465 | 2012-10-05 | 11 | 70:30 |  | FY 13-14 |  | FY 13-14 | [11 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | [15 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
0
| 16 | RInfra-G/DPR/BP11-16/DPR No 13 | Surrender |  | Tube Conveyor from Jetty to Coal Yard | MERC/Tech-IX/CAPEX/201202013/01540 | 2012-10-11 | 50 | 70:30 |  | FY 13-14 |  | FY 13-14 | [11 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0.19744 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 0.19744 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 17 | RInfra-G/DPR/BP11-16/DPR No 14 |  |  | Procurement and Installation of IP and LP Turbine Module in Unit # 2 | MERC/Tech-IX/CAPEX/12-13/02223 | 2013-01-03 | 96.28 | 70:30 |  | FY 13-14 |  | FY 15-16 |  |  | 31.2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.42% | 32.42% | 32.42% | 32.42% | 32.42% | 32.42% | 32.42% | 32.42% | 32.42% | 31.2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.13 | 208 | 30.13 | 0 | 0 | 30.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
42 | 17.1 | RInfra-G/DPR/BP11-16/DPR No 14.1 | Completed | Reliability Improvement | Procurement of spare IP Turbine module | MERC/Tech-IX/CAPEX/12-13/02223 | 2013-01-03 | 31.2 | 70:30 |  | FY 13-14 | FY 18-19 | FY 15-16 | FY 22-23 | 1. Efficiency Improvement | 31.2156 | FY23: 0; FY24: 0; Estimated FY25: 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 31.2156 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | [13 empty] | 30.13 | 36 | 30.13 |  |  | 30.13 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
178 | 17.2 | RInfra-G/DPR/BP11-16/DPR No 14.2 | Completed | Reliability Improvement | Procurement of spare LP Turbine module | MERC/Tech-IX/CAPEX/12-13/02223 | 2013-01-03 | 65.08 | 70:30 |  | FY 13-14 |  |  |  |  | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | [14 empty] | 172 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 45 | 45 |  |  | 45 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 45 | 0
[77 empty] | 0 | [6 empty] | 0
| 18 | RInfra-G/DPR/BP11-16/DPR No 16 |  |  | Bundled DPR for Non-DPR Capex schemes for Renovation & Modernization of Resubmitted Projects in 2nd MYT Control Period at DTPS | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 96.378 | 70:30 |  | FY 13-14 |  | FY 15-16 |  |  | 59.5662 | 1.0675 | 1.6552 | 0.22356 | 0 | 0 | 0 | 0 | 0 | 61.8% | 62.91% | 64.6% | 64.86% | 64.86% | 64.86% | 64.86% | 64.86% | 64.86% | 59.5585 | 1.0752 | 1.6287 | 0.25 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 31.3122 | 28.2665 | 1.0197 | 0 | 7.5522 | 0.19015 | 0 | 7.7424 | 2.1468 |  |  | 0 | 0 | 2.1468 | 0 | 5.3942 | 0.40543 | 0.23392 | 6.0335 | 0.54397 | 0.54397 | 1.3773 | 1213 | 1.9213 | 0 | 0 | 1.9213 | 0 | 0 | 2.86 | 3.36 | 0 | 0 | 3.36 | 0 | 0 | 1.15 | 2.07 | 0 | 0 | 2.07 | 0 | 0 | 0 | 0.7 | 0 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.36 | 2.07 | 0.7 | 0 | 0
| 18.1 | RInfra-G/DPR/BP11-16/DPR No 16.1 | Completed |  | Ash Utilisation Syetm | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 13.6 | 70:30 |  | FY 13-14 | FY 13-14 | FY 15-16 | FY 20-21 | 1. Statutory Complinace 2. Efficiency Improvement 3. Reliability Improvement 4. Safety Improvement 5. Energy Conservation | 3.8076 | FY23: 0; FY24: 0; Estimated FY25: 0 | 28% | 28% | 28% | 28% | 28% | 28% | 28% | 28% | 28% | 3.8076 | 0 | 0 | 0 | [7 empty] | Projects being completed in phase manner | [5 empty] | 0.79739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 |  | 0.25 | 0 | 0 | 0.25 | [6 empty] | 0 | [10 empty] | 0.5 | [6 empty] | 0 | [7 empty] | 0 | 0 | 0
| 18.1.1 | RInfra-G/DPR/BP11-16/DPR No 16.1.1 | Completed | Reliability Improvement | APH, Economizer and Duct Hoppers dry ash conveying system to Ash Grinding Unit | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 6 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.1.2 | RInfra-G/DPR/BP11-16/DPR No 16.1.2 | Completed | Reliability Improvement | Ash Storage Silo of Capacity Approximately 300MT | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 3 | 70:30 | [6 empty] | 2.595 | FY23: 0; FY24: 0; Estimated FY25: 0 | 86.5% | 86.5% | 86.5% | 86.5% | 86.5% | 86.5% | 86.5% | 86.5% | 86.5% | 2.595 | 0 | 0 | 0 | [13 empty] | 0.55997 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.1.3 | RInfra-G/DPR/BP11-16/DPR No 16.1.3 | Completed | Reliability Improvement | Ash Storage shed | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2 | 70:30 | [6 empty] | 0.6747 | FY23: 0; FY24: 0; Estimated FY25: 0 | 33.73% | 33.73% | 33.73% | 33.73% | 33.73% | 33.73% | 33.73% | 33.73% | 33.73% | 0.6747 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.1.4 | RInfra-G/DPR/BP11-16/DPR No 16.1.4 | Completed | Reliability Improvement | Ash bulker/ truck weigh bridge | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.6 | 70:30 | [6 empty] | 0.2756 | FY23: 0; FY24: 0; Estimated FY25: 0 | 45.93% | 45.93% | 45.93% | 45.93% | 45.93% | 45.93% | 45.93% | 45.93% | 45.93% | 0.2756 | 0 | 0 | 0 | [13 empty] | 0.23645 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
102 | 18.1.5 | RInfra-G/DPR/BP11-16/DPR No 16.1.5 | In Progress | Reliability Improvement | Strengthening of ash bridge steel structures | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2 | 70:30 | [6 empty] | 0.26233 | FY23: 0; FY24: 0; Estimated FY25: 0 | 13.12% | 13.12% | 13.12% | 13.12% | 13.12% | 13.12% | 13.12% | 13.12% | 13.12% | 0.26233 | 0 | 0 | 0 | [13 empty] | 0.00097554 | 0 | 0 |  |  |  |  | 0 | [13 empty] | 0.25 | 245 | 0.25 |  |  | 0.25 |  |  |  | 0 |  |  | 0 |  |  |  | 0.5 |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0.5 | 0.5 | 0 | 0
155 | 18.2 | RInfra-G/DPR/BP11-16/DPR No 16.2 | Completed | Reliability Improvement | Renovation of dewatering system | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.2 | 70:30 | [6 empty] | 0.08779 | FY23: 0; FY24: 0; Estimated FY25: 0 | 43.9% | 43.9% | 43.9% | 43.9% | 43.9% | 43.9% | 43.9% | 43.9% | 43.9% | 0.08779 | 0 | 0 | 0 | [13 empty] | 0.08779 | 0.08779 | 0 | [23 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.3 | RInfra-G/DPR/BP11-16/DPR No 16.3 | Completed | Reliability Improvement | Renovation of APH Seals with advanced brush seal | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.38 | 70:30 | [6 empty] | 0.328 | FY23: 0; FY24: 0; Estimated FY25: 0 | 86.32% | 86.32% | 86.32% | 86.32% | 86.32% | 86.32% | 86.32% | 86.32% | 86.32% | 0.328 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 | [23 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.4 | RInfra-G/DPR/BP11-16/DPR No 16.4 | Completed | Reliability Improvement | Procurement of Chemical Laboratory Analyzers | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.87236 | FY23: 0; FY24: 0; Estimated FY25: 0 | 87.24% | 87.24% | 87.24% | 87.24% | 87.24% | 87.24% | 87.24% | 87.24% | 87.24% | 0.87236 | 0 | 0 | 0 | [13 empty] | 0.46366 | 0.46366 | 0 | [23 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.5 | RInfra-G/DPR/BP11-16/DPR No 16.5 |  | Reliability Improvement | Renovation & Modernization of Bundled Non-DPR’s in to Revised DPR for C&I System at DTPS | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 17.65 | 70:30 | [6 empty] | 11.4549 | FY23: 0; FY24: 1.2998; Estimated FY25: 0 | 64.9% | 64.9% | 72.26% | 72.26% | 72.26% | 72.26% | 72.26% | 72.26% | 72.26% | 11.4549 | 0 | 1.2998 | 0 | [13 empty] | 6.7818 | 7.0229 | 0.0008015 | 0 | 1.6154 | 0.0044562 | 0 | 1.6199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.089008 | 0 | 0 | 0.089008 | 0 | 0 | 0.82734 |  | 0.82734 | 0 | 0 | 0.82734 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 | 0
126 | 18.5.1 | RInfra-G/DPR/BP11-16/DPR No 16.5.1 | Completed | Reliability Improvement | Renovation & Up-gradation of Gravimetric Feeders to Microprocessor Based system | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2.48 | 70:30 | [6 empty] | 1.1678 | FY23: 0; FY24: 1.2998; Estimated FY25: 0 | 47.09% | 47.09% | 99.5% | 99.5% | 99.5% | 99.5% | 99.5% | 99.5% | 99.5% | 1.1678 | 0 | 1.2998 | 0 | [13 empty] | 0.11592 | 0.11592 | 0 |  |  |  |  | 0 | [14 empty] | 120 | 0 |  |  | 0 |  |  | 1.21 | 1.21 |  |  | 1.21 |  |  | 1.15 | 1.15 |  |  | 1.15 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 1.21 | 1.15 | 0 | 0 | 0
127 | 18.5.2 | RInfra-G/DPR/BP11-16/DPR No 16.5.2 | Completed | Reliability Improvement | Renovation & Modernization of UPS, Battery and Battery chargers | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.99867 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.87% | 99.87% | 99.87% | 99.87% | 99.87% | 99.87% | 99.87% | 99.87% | 99.87% | 0.99867 | 0 | 0 | 0 | [13 empty] | 0.44231 | 0.44231 | 0 |  | 0.30782 | 0 |  | 0.30782 | [14 empty] | 121 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0.22 |  |  | 0.22 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0.22 | 0 | 0 | 0
| 18.5.3 | RInfra-G/DPR/BP11-16/DPR No 16.5.3 | Completed | Reliability Improvement | Procurement of CCTV for Boiler | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.3 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 | [6 empty] | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.5.4 | RInfra-G/DPR/BP11-16/DPR No 16.5.4 | Completed | Reliability Improvement | Renovation & Up-gradation of SWAS Analyzers for Steam & Water Analysis | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.5 | 70:30 | [6 empty] | 0.45247 | FY23: 0; FY24: 0; Estimated FY25: 0 | 90.49% | 90.49% | 90.49% | 90.49% | 90.49% | 90.49% | 90.49% | 90.49% | 90.49% | 0.45247 | 0 | 0 | 0 | [13 empty] | 0.39622 | 0.39622 | 0 |  | 0.05625 | 0 |  | 0.05625 | [18 empty] | 0 | [6 empty] | 0 | [9 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
93 | 18.5.5 | RInfra-G/DPR/BP11-16/DPR No 16.5.5 | Completed | Reliability Improvement | Renovation & Up-gradation of Flue Gas Analyzers | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.5 | 70:30 | [6 empty] | 1.3981 | FY23: 0; FY24: 0; Estimated FY25: 0 | 93.2% | 93.2% | 93.2% | 93.2% | 93.2% | 93.2% | 93.2% | 93.2% | 93.2% | 1.3981 | 0 | 0 | 0 | [13 empty] | 0.7761 | 0.7761 | 0 |  | 0.41784 | 0 |  | 0.41784 | [13 empty] | 0.12 | 87 | 0.12 |  |  | 0.12 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 18.5.6 | RInfra-G/DPR/BP11-16/DPR No 16.5.6 | Completed | Reliability Improvement | Up-gradation & Modernization of CO Analyzers | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.5 | 70:30 | [6 empty] | 1.4961 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.74% | 99.74% | 99.74% | 99.74% | 99.74% | 99.74% | 99.74% | 99.74% | 99.74% | 1.4961 | 0 | 0 | 0 | [13 empty] | 1.0455 | 1.0455 | 0 |  | 0.236 | 0 |  | 0.236 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
94 | 18.5.7 | RInfra-G/DPR/BP11-16/DPR No 16.5.7 | Completed | Reliability Improvement | Renovation & Modernization of H2 Purity analyzers | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.5 | 70:30 | [6 empty] | 0.46746 | FY23: 0; FY24: 0; Estimated FY25: 0 | 93.49% | 93.49% | 93.49% | 93.49% | 93.49% | 93.49% | 93.49% | 93.49% | 93.49% | 0.46746 | 0 | 0 | 0 | [13 empty] | 0.32583 | 0.32583 | 0 |  |  |  |  | 0 | [13 empty] | 0.18 | 88 | 0.18 |  |  | 0.18 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 18.5.8 | RInfra-G/DPR/BP11-16/DPR No 16.5.8 | Completed | Reliability Improvement | Renovation & Up-gradation of Field Instruments | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.5 | 70:30 | [6 empty] | 1.4599 | FY23: 0; FY24: 0; Estimated FY25: 0 | 97.33% | 97.33% | 97.33% | 97.33% | 97.33% | 97.33% | 97.33% | 97.33% | 97.33% | 1.4599 | 0 | 0 | 0 | [13 empty] | 0.9035 | 0.904 | 0 |  | 0.36623 | 0.0044562 |  | 0.37069 | [7 empty] | 0.089008 | 0 | 0 | 0.089008 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.5.9 | RInfra-G/DPR/BP11-16/DPR No 16.5.9 | Surrender |  | Renovation & Up-gradation of Vibration System in Unit-2 | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | -0.0031762 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
16 | 18.5.10 | RInfra-G/DPR/BP11-16/DPR No 16.5.10 | In Progress |  | Replacement of ID Fan Scoop controller (KE3) with Digital Control Drives | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.5 | 70:30 | [6 empty] | 0.25301 | FY23: 0; FY24: 0; Estimated FY25: 0 | 50.6% | 50.6% | 50.6% | 50.6% | 50.6% | 50.6% | 50.6% | 50.6% | 50.6% | 0.25301 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.12301 | 0 |  | 0.12301 | [13 empty] | 0.15 | 10 | 0.15 |  |  | 0.15 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 18.5.11 | RInfra-G/DPR/BP11-16/DPR No 16.5.11 | Completed |  | Up gradation of Master Clock for reliability improvement | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.15 | 70:30 | [6 empty] | 0.10826 | FY23: 0; FY24: 0; Estimated FY25: 0 | 72.17% | 72.17% | 72.17% | 72.17% | 72.17% | 72.17% | 72.17% | 72.17% | 72.17% | 0.10826 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.10825 | 0 |  | 0.10825 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.5.12 | RInfra-G/DPR/BP11-16/DPR No 16.5.12 | In Progress |  | Up-gradation of +24V battery set U#1 and UPS batteries at Switchyard | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.45 | 70:30 | [6 empty] | 0.24 | FY23: 0; FY24: 0; Estimated FY25: 0 | 53.33% | 53.33% | 53.33% | 53.33% | 53.33% | 53.33% | 53.33% | 53.33% | 53.33% | 0.24 | 0 | 0 | 0 | [13 empty] | 0.24 | 0.24 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
95 | 18.5.13 | RInfra-G/DPR/BP11-16/DPR No 16.5.13 | Completed |  | Up-gradation of Water flow meters in Kawdas Pump House and Plant area | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.15 | 70:30 | [6 empty] | 0.1372 | FY23: 0; FY24: 0; Estimated FY25: 0 | 91.47% | 91.47% | 91.47% | 91.47% | 91.47% | 91.47% | 91.47% | 91.47% | 91.47% | 0.1372 | 0 | 0 | 0 | [13 empty] | 0.096999 | 0.098589 | 0 |  |  |  |  | 0 | [13 empty] | 0.053001 | 89 | 0.053001 |  |  | 0.053001 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 18.5.14 | RInfra-G/DPR/BP11-16/DPR No 16.5.14 | Completed |  | Installation of Fire Alarm System at Coal Handling Plant | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.4 | 70:30 | [6 empty] | 0.4065 | FY23: 0; FY24: 0; Estimated FY25: 0 | 101.6% | 101.6% | 101.6% | 101.6% | 101.6% | 101.6% | 101.6% | 101.6% | 101.6% | 0.4065 | 0 | 0 | 0 | [13 empty] | 0.0008015 | 0 | 0.0008015 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.5.15 | RInfra-G/DPR/BP11-16/DPR No 16.5.15 | Completed |  | Up-gradation of Vibration Monitoring system for HT auxiliary | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.44844 | FY23: 0; FY24: 0; Estimated FY25: 0 | 44.84% | 44.84% | 44.84% | 44.84% | 44.84% | 44.84% | 44.84% | 44.84% | 44.84% | 0.44844 | 0 | 0 | 0 | [13 empty] | 0.44844 | 0.49759 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.5.16 | RInfra-G/DPR/BP11-16/DPR No 16.5.16 | In Progress |  | Up-gradation of Communication System | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.47566 | FY23: 0; FY24: 0; Estimated FY25: 0 | 47.57% | 47.57% | 47.57% | 47.57% | 47.57% | 47.57% | 47.57% | 47.57% | 47.57% | 0.47566 | 0 | 0 | 0 | [13 empty] | 0.4759 | 0.52871 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.5.17 | RInfra-G/DPR/BP11-16/DPR No 16.5.17 | Completed |  | Renovation and Up gradation of Low level Chloride Analyser. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.22 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
96 | 18.5.18 | RInfra-G/DPR/BP11-16/DPR No 16.5.18 | Completed |  | Procurement of CCTV system and Up gradation of existing LAN network for CCTV and Data management | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2 | 70:30 | [6 empty] | 1.9454 | FY23: 0; FY24: 0; Estimated FY25: 0 | 97.27% | 97.27% | 97.27% | 97.27% | 97.27% | 97.27% | 97.27% | 97.27% | 97.27% | 1.9454 | 0 | 0 | 0 | [13 empty] | 1.4257 | 1.5603 | 0 |  |  |  |  | 0 | [13 empty] | 0.32433 | 90 | 0.32433 |  |  | 0.32433 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 18.5.19 | RInfra-G/DPR/BP11-16/DPR No 16.5.19 | Completed |  | Renovation and Up gradation of Belt Weighing System | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0.0918 | 0.0918 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.6 | RInfra-G/DPR/BP11-16/DPR No 16.6 |  |  | Renovation & Modernization of Coal Handling System under NDPR Scheme | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 7.92 | 70:30 | [6 empty] | 6.2 | FY23: 0; FY24: 0; Estimated FY25: 0 | 78.28% | 78.28% | 78.28% | 78.28% | 78.28% | 78.28% | 78.28% | 78.28% | 78.28% | 6.2 | 0 | 0 | 0 | [13 empty] | 3.8365 | 3.7906 | 0 | 0 | 0.84471 | 0 | 0 | 0.84471 | 0.17654 | 0 | 0 | 0 | 0 | 0.17654 | 0 | 0.46015 | 0 | 0.019236 | 0.47939 | 0 | 0 | 0.3 |  | 0.3 | 0 | 0 | 0.3 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0
40 | 18.6.1 | RInfra-G/DPR/BP11-16/DPR No 16.6.1 | Completed |  | Renovation & Modernization of Wagon Tippler Drive system | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.64931 | FY23: 0; FY24: 0; Estimated FY25: 0 | 64.93% | 64.93% | 64.93% | 64.93% | 64.93% | 64.93% | 64.93% | 64.93% | 64.93% | 0.64931 | 0 | 0 | 0 | [13 empty] | 0.35328 | 0.35328 | 0 |  |  |  |  | 0 | [10 empty] | 0 |  |  | 0.3 | 34 | 0.3 |  |  | 0.3 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 18.6.2 | RInfra-G/DPR/BP11-16/DPR No 16.6.2 | Completed |  | Renovation of Wagon Tippler and associated equipments | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.65 | 70:30 | [6 empty] | 2.0586 | FY23: 0; FY24: 0; Estimated FY25: 0 | 124.8% | 124.8% | 124.8% | 124.8% | 124.8% | 124.8% | 124.8% | 124.8% | 124.8% | 2.0586 | 0 | 0 | 0 | [13 empty] | 1.3758 | 1.3758 | 0 |  | 0.37496 | 0 |  | 0.37496 | [10 empty] | 0 |  |  |  | 16 | 0 |  |  | 0 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.5 | 0 | 0 | 0 | 0
| 18.6.3 | RInfra-G/DPR/BP11-16/DPR No 16.6.3 | Completed |  | Renovation of Locomotive | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.35 | 70:30 | [6 empty] | 1.3467 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.75% | 99.75% | 99.75% | 99.75% | 99.75% | 99.75% | 99.75% | 99.75% | 99.75% | 1.3467 | 0 | 0 | 0 | [13 empty] | 0.57943 | 0.5897 | 0 |  |  |  |  | 0 | 0.17654 |  |  |  |  | 0.17654 |  | 0.46015 | 0 | 0.019236 | 0.47939 | [7 empty] | 0 | [6 empty] | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.6.4 | RInfra-G/DPR/BP11-16/DPR No 16.6.4 | Completed |  | Renovation of Travelling Trolley | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.22 | 70:30 | [6 empty] | 0.28 | FY23: 0; FY24: 0; Estimated FY25: 0 | 127.3% | 127.3% | 127.3% | 127.3% | 127.3% | 127.3% | 127.3% | 127.3% | 127.3% | 0.28 | 0 | 0 | 0 | [13 empty] | 0.28 | 0.28 | 0 |  |  |  |  | 0 | [10 empty] | 0 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.6.5 | RInfra-G/DPR/BP11-16/DPR No 16.6.5 | Completed |  | Renovation & Modernization of existing Dust Extraction system & Dust Suppression system. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.5 | 70:30 | [6 empty] | 0.75201 | FY23: 0; FY24: 0; Estimated FY25: 0 | 50.13% | 50.13% | 50.13% | 50.13% | 50.13% | 50.13% | 50.13% | 50.13% | 50.13% | 0.75201 | 0 | 0 | 0 | [13 empty] | 0.28226 | 0.28226 | 0 |  | 0.46976 | 0 |  | 0.46976 | [10 empty] | 0 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.6.6 | RInfra-G/DPR/BP11-16/DPR No 16.6.6 | Completed |  | Deep screening & renovation of DTPS Rail Track Siding. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.2 | 70:30 | [6 empty] | 1.1133 | FY23: 0; FY24: 0; Estimated FY25: 0 | 92.77% | 92.77% | 92.77% | 92.77% | 92.77% | 92.77% | 92.77% | 92.77% | 92.77% | 1.1133 | 0 | 0 | 0 | [13 empty] | 0.96578 | 0.90957 | 0 |  |  |  |  | 0 | [10 empty] | 0 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.6.7 | RInfra-G/DPR/BP11-16/DPR No 16.6.7 | Completed |  | Maintenance shed for dozers and Loaders | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [10 empty] | 0 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.7 | RInfra-G/DPR/BP11-16/DPR No 16.7 |  |  | Refurbishment of Civil structures based on Residual Life Assessment (RLA) Study | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 7.75 | 70:30 | [6 empty] | 8.591 | FY23: 0; FY24: 0; Estimated FY25: 0 | 110.9% | 110.9% | 110.9% | 110.9% | 110.9% | 110.9% | 110.9% | 110.9% | 110.9% | 8.591 | 0 | 0 | 0 | [13 empty] | 5.0775 | 4.0029 | 0 |  | 0.648 | 0.015877 | 0 | 0.66388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0
| 18.7.1 | RInfra-G/DPR/BP11-16/DPR No 16.7.1 | Completed |  | Renovation of CHP tunnels based on Residual Life Assessment (RLA) Study | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 3 | 70:30 | [6 empty] | 3.6193 | FY23: 0; FY24: 0; Estimated FY25: 0 | 120.6% | 120.6% | 120.6% | 120.6% | 120.6% | 120.6% | 120.6% | 120.6% | 120.6% | 3.6193 | 0 | 0 | 0 | [13 empty] | 3.3109 | 3.1329 | 0 |  | 0.648 | 0.015877 |  | 0.66388 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.7.2 | RInfra-G/DPR/BP11-16/DPR No 16.7.2 | Completed |  | Refurbishment of Railway Bridge, Road Bridge & Overhead water tank based on Residual Life Assessment (RLA) Study. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.25 | 70:30 | [6 empty] | 0.9936 | FY23: 0; FY24: 0; Estimated FY25: 0 | 79.49% | 79.49% | 79.49% | 79.49% | 79.49% | 79.49% | 79.49% | 79.49% | 79.49% | 0.9936 | 0 | 0 | 0 | [13 empty] | 0.6981 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.7.3 | RInfra-G/DPR/BP11-16/DPR No 16.7.3 | Completed |  | Renovation of CW Pump House based on Residual Life Assessment (RLA) Study. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.5 | 70:30 | [6 empty] | 0.4547 | FY23: 0; FY24: 0; Estimated FY25: 0 | 90.94% | 90.94% | 90.94% | 90.94% | 90.94% | 90.94% | 90.94% | 90.94% | 90.94% | 0.4547 | 0 | 0 | 0 | [13 empty] | 0.19716 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.7.4 | RInfra-G/DPR/BP11-16/DPR No 16.7.4 | Completed |  | Renovation of CHP Civil Foundations, Structures and Buildings based on Residual Life Assessment (RLA) Study. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 3 | 70:30 | [6 empty] | 3.5235 | FY23: 0; FY24: 0; Estimated FY25: 0 | 117.4% | 117.4% | 117.4% | 117.4% | 117.4% | 117.4% | 117.4% | 117.4% | 117.4% | 3.5235 | 0 | 0 | 0 | [13 empty] | 0.87127 | 0.87007 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.8 | RInfra-G/DPR/BP11-16/DPR No 16.8 | Completed |  | Construction of jackwell and pump house in Kawdas | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2.38 | 70:30 | [6 empty] | 2.3799 | FY23: 0; FY24: 0; Estimated FY25: 0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 2.3799 | 0 | 0 | 0 | [13 empty] | 0.21118 | 0 | 0 |  | 0 |  |  | 0 | 0 |  |  |  |  | 0 | [12 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9 | RInfra-G/DPR/BP11-16/DPR No 16.9 |  |  | Civil Works at Dahanu TPS | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 25.55 | 70:30 | [6 empty] | 19.6675 | FY23: 0.95709; FY24: 0; Estimated FY25: 0 | 76.95% | 80.72% | 80.72% | 80.72% | 80.72% | 80.72% | 80.72% | 80.72% | 80.72% | 19.6597 | 0.96482 | 0 | 0 | [13 empty] | 10.6683 | 9.4916 | 0.97913 | 0 | 3.0056 | 0.096919 | 0 | 3.1026 | 1.8837 | 0 | 0 | 0 | 0 | 1.8837 | 0 | 4.6549 | 0.39139 | 0.20525 | 5.2515 | 0.54397 | 0.54397 | 0 |  | 0.54397 | 0 | 0 | 0.54397 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 | 0
| 18.9.1 | RInfra-G/DPR/BP11-16/DPR No 16.9.1 | Completed |  | Refurbishment of Bituminous Road with paver finish at Plant area | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2.5 | 70:30 | [6 empty] | 2.988 | FY23: 0; FY24: 0; Estimated FY25: 0 | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 119.5% | 2.988 | 0 | 0 | 0 | [13 empty] | 2.263 | 2.263 | 0 |  |  |  |  | 0 | [7 empty] | 0.725 | 0.061377 | 0 | 0.78638 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.2 | RInfra-G/DPR/BP11-16/DPR No 16.9.2 | Completed |  | Raising height of Ash bund for Ash storage and subsequent utilization | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 4.86 | 70:30 | [6 empty] | 6.535 | FY23: 0; FY24: 0; Estimated FY25: 0 | 134.5% | 134.5% | 134.5% | 134.5% | 134.5% | 134.5% | 134.5% | 134.5% | 134.5% | 6.535 | 0 | 0 | 0 | [13 empty] | 2.6369 | 2.753 | 0 |  |  |  |  | 0 | 1.852 |  |  |  |  | 1.852 |  | 3.8982 | 0.33001 | 0.2018 | 4.43 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.3 | RInfra-G/DPR/BP11-16/DPR No 16.9.3 | Completed |  | Strengthening of Buildings in Plant. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.6 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.4 | RInfra-G/DPR/BP11-16/DPR No 16.9.4 | Completed |  | Strengthening of Cladding at Power House Building. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.8 | 70:30 | [6 empty] | 0.35255 | FY23: 0.34122; FY24: 0; Estimated FY25: 0 | 44.07% | 86.72% | 86.72% | 86.72% | 86.72% | 86.72% | 86.72% | 86.72% | 86.72% | 0.35255 | 0.34122 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.5 | RInfra-G/DPR/BP11-16/DPR No 16.9.5 | Completed |  | Water-proofing of Buildings | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.6 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.6 | RInfra-G/DPR/BP11-16/DPR No 16.9.6 | Completed |  | Strengthening of Plant roads for smooth vehicular movement | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2.2 | 70:30 | [6 empty] | 1.6806 | FY23: 0; FY24: 0; Estimated FY25: 0 | 76.39% | 76.39% | 76.39% | 76.39% | 76.39% | 76.39% | 76.39% | 76.39% | 76.39% | 1.6806 | 0 | 0 | 0 | [13 empty] | 1.4263 | 1.5899 | 0 |  | 0.24048 | 0.013234 |  | 0.25371 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.7 | RInfra-G/DPR/BP11-16/DPR No 16.9.7 | Completed |  | Up gradation of storm water drains in Plant | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.8 | 70:30 | [6 empty] | 0.62193 | FY23: 0; FY24: 0; Estimated FY25: 0 | 77.74% | 77.74% | 77.74% | 77.74% | 77.74% | 77.74% | 77.74% | 77.74% | 77.74% | 0.62193 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0.0023938 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.8 | RInfra-G/DPR/BP11-16/DPR No 16.9.8 | Completed |  | Ash pond area Security enhancement | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.85 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [11 empty] | 0.54397 | 0.54397 | 0 |  | 0.54397 |  |  | 0.54397 | 0 |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.9 | RInfra-G/DPR/BP11-16/DPR No 16.9.9 | Completed |  | Removal of deposition in Water Holding Ponds | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.5 | 70:30 | [6 empty] | 0.23887 | FY23: 0; FY24: 0; Estimated FY25: 0 | 15.92% | 15.92% | 15.92% | 15.92% | 15.92% | 15.92% | 15.92% | 15.92% | 15.92% | 0.23887 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.23887 | 0 |  | 0.23887 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.10 | RInfra-G/DPR/BP11-16/DPR No 16.9.10 | Completed |  | Widening of Mota Pada Road | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.11 | RInfra-G/DPR/BP11-16/DPR No 16.9.11 | Completed |  | Construction of Peripheral Road along the fence in plant area for security patrolling | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.75 | 70:30 | [6 empty] | 0.68869 | FY23: 0; FY24: 0; Estimated FY25: 0 | 91.82% | 91.82% | 91.82% | 91.82% | 91.82% | 91.82% | 91.82% | 91.82% | 91.82% | 0.68869 | 0 | 0 | 0 | [13 empty] | 0.68869 | 0.68869 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.12 | RInfra-G/DPR/BP11-16/DPR No 16.9.12 | Completed |  | Refurbishment of cable trench at Switchyard | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.4 | 70:30 | [6 empty] | 0.36828 | FY23: 0; FY24: 0; Estimated FY25: 0 | 92.07% | 92.07% | 92.07% | 92.07% | 92.07% | 92.07% | 92.07% | 92.07% | 92.07% | 0.36828 | 0 | 0 | 0 | [13 empty] | 0.36825 | 0.38476 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.13 | RInfra-G/DPR/BP11-16/DPR No 16.9.13 | Completed |  | Replacement of Water supply lines for Reliability Improvement | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.7 | 70:30 | [6 empty] | 0.8868 | FY23: 0; FY24: 0; Estimated FY25: 0 | 126.7% | 126.7% | 126.7% | 126.7% | 126.7% | 126.7% | 126.7% | 126.7% | 126.7% | 0.8868 | 0 | 0 | 0 | [13 empty] | 0.52438 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.14 | RInfra-G/DPR/BP11-16/DPR No 16.9.14 | Completed |  | Up gradation of STP Sewerage System | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.1 | 70:30 | [6 empty] | 0.8117 | FY23: 0; FY24: 0; Estimated FY25: 0 | 73.79% | 73.79% | 73.79% | 73.79% | 73.79% | 73.79% | 73.79% | 73.79% | 73.79% | 0.8117 | 0 | 0 | 0 | [13 empty] | 0.81213 | 0.83243 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.15 | RInfra-G/DPR/BP11-16/DPR No 16.9.15 | In Progress |  | Renovation and Modernization of Offices, Canteen etc | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1.7 | 70:30 | [6 empty] | 1.0108 | FY23: 0.25363; FY24: 0; Estimated FY25: 0 | 59% | 74.38% | 74.38% | 74.38% | 74.38% | 74.38% | 74.38% | 74.38% | 74.38% | 1.0031 | 0.26136 | 0 | 0 | [13 empty] | 0.49769 | 0.49038 | 0.012159 |  | 0.48618 | 0.0020851 |  | 0.48827 | 0.031664 |  |  |  |  | 0.031664 |  | 0.031664 | 0 | 0.0034502 | 0.035114 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.16 | RInfra-G/DPR/BP11-16/DPR No 16.9.16 | In Progress |  | Main Plant Security Gate Renovation for Safety Enhancement | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.25 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.17 | RInfra-G/DPR/BP11-16/DPR No 16.9.17 | Completed |  | Renovation of Shut Down sheds | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.8685 | FY23: 0; FY24: 0; Estimated FY25: 0 | 86.85% | 86.85% | 86.85% | 86.85% | 86.85% | 86.85% | 86.85% | 86.85% | 86.85% | 0.8685 | 0 | 0 | 0 | [13 empty] | 0.48647 | 0.48949 | 0 |  | 0.37901 | 0.0031985 |  | 0.38221 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.9.18 | RInfra-G/DPR/BP11-16/DPR No 16.9.18 | Completed |  | Construction of Coal Settlement containment pit in Holding Pond | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.5 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
81 | 18.9.19 | RInfra-G/DPR/BP11-16/DPR No 16.9.19 | Completed |  | Replacement of AC sheet by Colour Coated Galvalume Sheet at CHP Conveyor gantry, W Tippler, Auto Base etc. | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2.94 | 70:30 | [6 empty] | 2.6158 | FY23: 0.36224; FY24: 0; Estimated FY25: 0 | 88.97% | 101.3% | 101.3% | 101.3% | 101.3% | 101.3% | 101.3% | 101.3% | 101.3% | 2.6158 | 0.36224 | 0 | 0 | [13 empty] | 0.96457 | 0 | 0.96457 |  | 1.6611 | 0.078401 |  | 1.7395 | [14 empty] | 75 | 0 |  |  | 0 |  |  | 0.75 | 0.75 |  |  | 0.75 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.75 | 0 | 0 | 0 | 0
| 18.1 | RInfra-G/DPR/BP11-16/DPR No 16.10 |  |  | Enery Conservation Projects | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.51088 | FY23: 0; FY24: 0; Estimated FY25: 0 | 51.09% | 51.09% | 51.09% | 51.09% | 51.09% | 51.09% | 51.09% | 51.09% | 51.09% | 0.51088 | 0 | 0 | 0 | [13 empty] | 0.41998 | 0.41998 | 0 | 0 | 0.0125 | 0 | 0 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0784 | 0 | 0 | 0.0784 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 | 0
| 18.10.1 | RInfra-G/DPR/BP11-16/DPR No 16.10.1 | Completed |  | Installation of VFD in LT Drives | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.25 | 70:30 | [6 empty] | 0.2509 | FY23: 0; FY24: 0; Estimated FY25: 0 | 100.4% | 100.4% | 100.4% | 100.4% | 100.4% | 100.4% | 100.4% | 100.4% | 100.4% | 0.2509 | 0 | 0 | 0 | [13 empty] | 0.16 | 0.16 | 0 |  | 0.0125 | 0 |  | 0.0125 | [7 empty] | 0.0784 | 0 | 0 | 0.0784 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.10.2 | RInfra-G/DPR/BP11-16/DPR No 16.10.2 | Completed |  | Renovation of Electrical Heater System for Compressed Air | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.25 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.10.3 | RInfra-G/DPR/BP11-16/DPR No 16.10.3 | Completed |  | Renovation & Modernization of Chimney, Boiler & TG Unit 2 Elevators | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.5 | 70:30 | [6 empty] | 0.25998 | FY23: 0; FY24: 0; Estimated FY25: 0 | 52% | 52% | 52% | 52% | 52% | 52% | 52% | 52% | 52% | 0.25998 | 0 | 0 | 0 | [13 empty] | 0.25998 | 0.25998 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.11 | RInfra-G/DPR/BP11-16/DPR No 16.11 | Completed |  | Renovation & Modernisation of 220KV switchyard Battery | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.058 | 70:30 | [6 empty] | 0.06464 | FY23: 0; FY24: 0; Estimated FY25: 0 | 111.4% | 111.4% | 111.4% | 111.4% | 111.4% | 111.4% | 111.4% | 111.4% | 111.4% | 0.06464 | 0 | 0 | 0 | [13 empty] | 0.06464 | 0.06464 | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.12 | RInfra-G/DPR/BP11-16/DPR No 16.12 |  |  | Mechanical Revised DPR from NDPR | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 3.34 | 70:30 | [6 empty] | 1.8812 | FY23: 0; FY24: 0; Estimated FY25: 0 | 56.32% | 56.32% | 56.32% | 56.32% | 56.32% | 56.32% | 56.32% | 56.32% | 56.32% | 1.8812 | 0 | 0 | 0 | [13 empty] | 2.0676 | 2.0509 | 0.034643 | 0 | 0.10332 | 0.0026009 | 0 | 0.10592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 | 0
| 18.12.1 | RInfra-G/DPR/BP11-16/DPR No 16.12.1 | Completed |  | Refurbishment of Boiler Insulation to prevent heat loss | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.41 | 70:30 | [6 empty] | 0.18768 | FY23: 0; FY24: 0; Estimated FY25: 0 | 45.77% | 45.77% | 45.77% | 45.77% | 45.77% | 45.77% | 45.77% | 45.77% | 45.77% | 0.18768 | 0 | 0 | 0 | [13 empty] | 0.44157 | 0.45044 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.12.2 | RInfra-G/DPR/BP11-16/DPR No 16.12.2 | Completed |  | Auxiliary reducer gear box for coal mill to improve reliability and availability of coal mills | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.33 | 70:30 | [6 empty] | 0.33059 | FY23: 0; FY24: 0; Estimated FY25: 0 | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 100.2% | 0.33059 | 0 | 0 | 0 | [13 empty] | 0.33059 | 0.33059 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.12.3 | RInfra-G/DPR/BP11-16/DPR No 16.12.3 | Completed |  | Strengthening of firefighting System | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.6 | 70:30 | [6 empty] | 0.59832 | FY23: 0; FY24: 0; Estimated FY25: 0 | 99.72% | 99.72% | 99.72% | 99.72% | 99.72% | 99.72% | 99.72% | 99.72% | 99.72% | 0.59832 | 0 | 0 | 0 | [13 empty] | 0.53079 | 0.50528 | 0.034643 |  | 0.10332 | 0.0026009 |  | 0.10592 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.12.4 | RInfra-G/DPR/BP11-16/DPR No 16.12.4 | Surrender |  | Renovation of raw water system | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.12.5 | RInfra-G/DPR/BP11-16/DPR No 16.12.5 | Completed |  | Hydrogen generation plant | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 1 | 70:30 | [6 empty] | 0.7646 | FY23: 0; FY24: 0; Estimated FY25: 0 | 76.46% | 76.46% | 76.46% | 76.46% | 76.46% | 76.46% | 76.46% | 76.46% | 76.46% | 0.7646 | 0 | 0 | 0 | [13 empty] | 0.7646 | 0.7646 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
19 | 18.13 | RInfra-G/DPR/BP11-16/DPR No 16.13 | Completed |  | Renovation of Turbine Compensators in Renovation & Modernization of Turbines | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 9 | 70:30 | [6 empty] | 0.85409 | FY23: 0; FY24: 0; Estimated FY25: 0 | 9.49% | 9.49% | 9.49% | 9.49% | 9.49% | 9.49% | 9.49% | 9.49% | 9.49% | 0.85409 | 0 | 0 | 0 | [13 empty] | 0.0051675 | 0 | 0.0051675 |  | 0.85409 | 0.064121 |  | 0.91821 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
133 | 18.14 | RInfra-G/DPR/BP11-16/DPR No 16.14 | In Progress |  | Renovation & Modernization of Air Handling Units and Ventilation Fans | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 3 | 70:30 | [6 empty] | 1.5599 | FY23: 0.1104; FY24: 0.12539; Estimated FY25: 0.22356 | 52% | 55.68% | 58.97% | 67.31% | 67.31% | 67.31% | 67.31% | 67.31% | 67.31% | 1.5599 | 0.1104 | 0.098951 | 0.25 | [13 empty] | 0.19769 | 0.21399 | 0 |  | 0.41893 | 0.0061762 |  | 0.42511 | 0.086534 |  |  |  |  | 0.086534 |  | 0.11173 | 0.014042 | 0.0094289 | 0.1352 |  |  |  | 140 | 0 |  |  | 0 |  |  | 0.6 | 0.6 |  |  | 0.6 |  |  |  | 0.2 |  |  | 0.2 |  |  |  | 0.2 |  |  | 0.2 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.6 | 0.2 | 0.2 | 0 | 0
| 18.15 | RInfra-G/DPR/BP11-16/DPR No 16.15 | In Progress |  | Procurement of FFT & Ultrasonic Analyzers | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.8 | 70:30 | [6 empty] | 0.629 | FY23: 0; FY24: 0; Estimated FY25: 0 | 78.62% | 78.62% | 78.62% | 78.62% | 78.62% | 78.62% | 78.62% | 78.62% | 78.62% | 0.629 | 0 | 0 | 0 | [13 empty] | 0.63302 | 0.65755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | [10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 | 0
| 18.15.1 | RInfra-G/DPR/BP11-16/DPR No 16.15.1 | Completed |  | Procurement of Advanced FFT Vibration Analyzer (CSI 2130) | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.65 | 70:30 | [6 empty] | 0.629 | FY23: 0; FY24: 0; Estimated FY25: 0 | 96.77% | 96.77% | 96.77% | 96.77% | 96.77% | 96.77% | 96.77% | 96.77% | 96.77% | 0.629 | 0 | 0 | 0 | [13 empty] | 0.63302 | 0.65755 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| 18.15.2 | RInfra-G/DPR/BP11-16/DPR No 16.15.2 | In Progress |  | Procurement of New Effective Ultrasonic Monitoring Analyzer | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.15 | 70:30 | [6 empty] | 0 | FY23: 0; FY24: 0; Estimated FY25: 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [18 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
104 | 18.16 | RInfra-G/DPR/BP11-16/DPR No 16.16 | In Progress |  | Procurement of Online & Wireless vibration monitoring System | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 0.7 | 70:30 | [6 empty] | 0.51011 | FY23: 0; FY24: 0.23; Estimated FY25: 0 | 72.87% | 72.87% | 105.7% | 105.7% | 105.7% | 105.7% | 105.7% | 105.7% | 105.7% | 0.51011 | 0 | 0.23 | 0 | [13 empty] | 0 | 0 | 0 |  | 0.04962 | 0 |  | 0.04962 | [14 empty] | 98 | 0 |  |  | 0 |  |  | 0.3 | 0.3 |  |  | 0.3 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.3 | 0 | 0 | 0 | 0
| 18.17 | RInfra-G/DPR/BP11-16/DPR No 16.17 | In Progress |  | Spillage Oil Recovery system from Creek and Sea | MERC/Tech-IX/CAPEX/2014-15/00085 | 2014-04-10 | 2.05 | 70:30 | [6 empty] | 0.16738 | FY23: 0; FY24: 0; Estimated FY25: 0 | 8.165% | 8.165% | 8.165% | 8.165% | 8.165% | 8.165% | 8.165% | 8.165% | 8.165% | 0.16738 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 0 | [12 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[77 empty] | 0 | [6 empty] | 0
| 19 | RInfra-G/DPR/BP11-16/DPR No 17 | Completed |  | Complete Renovation of High Pressure Turbine Module DTPS | MERC/Cell No.1/CAPEX/20152016/00633 | 2015-09-09 | 25.96 | 70:30 |  | FY15-16 |  | FY 16-17 | FY 18-19 | 1. Efficiency Improvement | 18.05 | [8 empty] | 69.53% | 69.53% | 69.53% | 69.53% | 69.53% | 69.53% | 69.53% | 69.53% | 69.53% | 18.05 | 0 | 0 | 0 | [13 empty] | 0.32644 | 0 | 0.27856 |  | 17.337 | 0.056898 |  | 17.3939 |  |  |  | 0.32644 | 0 | 0 |  | 0.71326 | 0.089644 | 0 | 0.8029 | [10 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
132 | 20 | RInfra-G/DPR/BP11-16/DPR No 18 | In Progress |  | Complete Rewinding of Generator stator unit 2 DTPS | MERC/Cell No.1/CAPEX/20152016/00633 | 2015-09-09 | 19.71 | 70:30 |  | FY15-16 |  | FY 16-17 | FY 19-20 | 1. Reliability Improvement | 15.5355 | [8 empty] | 78.82% | 78.82% | 78.82% | 78.82% | 78.82% | 78.82% | 78.82% | 78.82% | 78.82% | 15.5355 | 0 | 0 | 0 | [13 empty] | 0 | 0 | 0 |  | 14.767 | 0 |  | 14.767 |  |  |  | 0 | 0 | 0 |  | 0.76855 | 0 | 0 | 0.76855 | [10 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
180 | 21 | RInfra-G/DPR/BP11-16/DPR No 19 | In Progress |  | R&M of Rail Track System DTPS | MERC/Cell No.1/CAPEX/20152016/00633 | 2015-09-09 | 11 | 70:30 |  | FY15-16 |  | FY 18-19 | FY 20-21 | 1. Safety Improvement 2. Reliability Improvement | 3.3809 | [8 empty] | 30.74% | 30.74% | 30.74% | 30.74% | 30.74% | 30.74% | 30.74% | 30.74% | 30.74% | 3.3809 | 0 | 0 | 0 | [13 empty] | 2.9455 | 2.9455 | 0 |  | 0.43539 | 0 |  | 0.43539 |  |  |  | 2.9455 | 2.9455 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 300 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0.5 | 0.5 |  |  | 0.5 |  |  | 2 | 2 |  |  | 2 |  |  | 2 | 2 |  |  |  | 2 | 0 | 0 | 0.5 | 2 | 2
| 22 | Schemes |  |  | Urgent approval of DPR |  |  | 22.78 | 70:30 |  | FY 17-18 |  | FY 19-20 |  |  | 20.4438 | 0 | 0.11759 | 0 | 0 | 0 | 0 | 0 | 0 | 89.74% | 89.74% | 90.26% | 90.26% | 90.26% | 90.26% | 90.26% | 90.26% | 90.26% | 20.4438 | 0 | 0.11759 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 6.809 | 0 | 0 | 6.809 | 0.052033 | 0 |  | 0 | 0 | 0.052033 | 0 | 9.0291 | 0.83187 | 0.025302 | 9.8862 | 1.0364 | 1.0364 | 0.00033593 | 90 | 1.05 | 0 | 0 | 1.05 | 0 | 0 | 4.1618 | 5.112 | 0 | 0 | 5.112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.112 | 0 | 0 | 0 | 0
|  | Scheme 1 | In Progress |  | Refurbishment of Air Pre heater | MERC/CAPEX/20162017/01825 | 2017-04-11 | 10 | 70:30 |  | FY 17-18 | FY 17-18 | FY 19-20 | FY 21-22 | 1. Reliability Improvement 2. Satutory Complaince 3. Energy Conservation 4. Efficiency Improvement | 7.2122 | FY23: 0; FY24: 0.11759; Estimated FY25: 0 | 72.12% | 72.12% | 73.3% | 73.3% | 73.3% | 73.3% | 73.3% | 73.3% | 73.3% | 7.2122 | 0 | 0.11759 | 0 | [17 empty] | 3.5851 | 0 |  | 3.5851 | 0.052033 |  |  |  |  | 0.052033 |  | 3.5538 | 0.44011 | 0.0056697 | 3.9996 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
61 |  | Scheme 2 | Completed |  | Refurbishmnet of Milling system | MERC/CAPEX/20162017/01825 | 2017-04-11 | 1 | 70:30 | [6 empty] | 1.2155 | FY23: 0; FY24: 0; Estimated FY25: 0 | 121.5% | 121.5% | 121.5% | 121.5% | 121.5% | 121.5% | 121.5% | 121.5% | 121.5% | 1.2155 | 0 | 0 | 0 | [17 empty] | 0.18391 | 0 |  | 0.18391 | [7 empty] | 0.35948 | 0.04518 | 0.00032489 | 0.40498 | 0.44747 | 0.44747 | 0.0025313 | 55 | 0.45 |  |  | 0.45 | 0 |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Scheme No -3 | Completed |  | Refurbishment of Gas to gas heater of Unit 1 | MERC/CAPEX/20162017/01825 | 2017-04-11 | 4 | 70:30 | [6 empty] | 4.4432 | FY23: 0; FY24: 0; Estimated FY25: 0 | 111.1% | 111.1% | 111.1% | 111.1% | 111.1% | 111.1% | 111.1% | 111.1% | 111.1% | 4.4432 | 0 | 0 | 0 | [17 empty] | 2.2332 | 0 |  | 2.2332 | [7 empty] | 2.2102 | 0.27779 | 0 | 2.488 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Scheme No -6 | Completed |  | Refurbishment of CW Pumps | MERC/CAPEX/20162017/01825 | 2017-04-11 | 0.6 | 70:30 | [6 empty] | 0.95819 | FY23: 0; FY24: 0; Estimated FY25: 0 | 159.7% | 159.7% | 159.7% | 159.7% | 159.7% | 159.7% | 159.7% | 159.7% | 159.7% | 0.95819 | 0 | 0 | 0 | [17 empty] | 0.41519 | 0 |  | 0.41519 | [7 empty] | 0.5473 | 0.068785 | 0.0072711 | 0.62335 | [7 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
35 |  | Scheme No -7 | Completed |  | Replacement of MV/LT VFD | MERC/CAPEX/20162017/01825 | 2017-04-11 | 0.68 | 70:30 | [6 empty] | 0.39154 | FY23: 0; FY24: 0; Estimated FY25: 0 | 57.58% | 57.58% | 57.58% | 57.58% | 57.58% | 57.58% | 57.58% | 57.58% | 57.58% | 0.39154 | 0 | 0 | 0 | [17 empty] | 0.39154 | 0 |  | 0.39154 | [14 empty] | 29 | 0.6 |  |  | 0.6 |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Scheme No -9 | Completed |  | Refurbishment of Turbine Valves | MERC/CAPEX/20162017/01825 | 2017-04-11 | 3.5 | 70:30 | [6 empty] | 3.3167 | FY23: 0; FY24: 0; Estimated FY25: 0 | 94.76% | 94.76% | 94.76% | 94.76% | 94.76% | 94.76% | 94.76% | 94.76% | 94.76% | 3.3167 | 0 | 0 | 0 | [20 empty] | 0 | [7 empty] | 2.3582 | 0 | 0.012036 | 2.3702 |  |  |  | 2 | 0 |  |  | 0 |  |  | 2.3363 | 2.3363 |  |  | 2.3363 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 2.3363 | 0 | 0 | 0 | 0
7 |  | Scheme No -10 | Completed |  | Refurbishment of HP bypass / LP bypass and sparay valves BFP recirculation pressure reducing & desuperheating stations(PRDS) | MERC/CAPEX/20162017/01825 | 2017-04-11 | 2 | 70:30 | [6 empty] | 1.8926 | FY23: 0; FY24: 0; Estimated FY25: 0 | 94.63% | 94.63% | 94.63% | 94.63% | 94.63% | 94.63% | 94.63% | 94.63% | 94.63% | 1.8926 | 0 | 0 | 0 | [20 empty] | 0 | [11 empty] | 0.0021954 | 0.0021954 | -0.0021954 | 1 | 0 |  |  | 0 | 0 | 0 | 1.8255 | 1.8255 |  |  | 1.8255 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 1.8255 | 0 | 0 | 0 | 0
9 |  | Scheme No -11 | Completed |  | Refubishment of turbine gland sealing system | MERC/CAPEX/20162017/01825 | 2017-04-11 | 1 | 70:30 | [6 empty] | 1.0138 | FY23: 0; FY24: 0; Estimated FY25: 0 | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 1.0138 | 0 | 0 | 0 | [20 empty] | 0 | [11 empty] | 0.58678 | 0.58678 |  | 3 |  |  |  | 0 |  |  |  | 0.95014 |  |  | 0.95014 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.95014 | 0 | 0 | 0 | 0
[77 empty] | 0 | [6 empty] | 0
| 23 | RInfra-G/DPR/BP18-24/DPR No. 26 |  |  | Refurbishment of Boiler and Auxiliaries |  |  | 67.48 | 70:30 |  | FY 18-19 |  | FY 22-23 |  |  | 4.9278 | 1.7241 | 0.476 | 0.32 | 0 | 0 | 0 | 0 | 0 | 7.158% | 9.665% | 10.4% | 10.88% | 10.88% | 10.88% | 10.88% | 10.88% | 10.88% | 4.8304 | 1.6913 | 0.49673 | 0.32 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0.46354 | 0.058259 | 0 | 0.5218 | 0 | 0 | 0.55 | 272 | 0.55 | 0 | 0 | 0.55 | 0 | 0 | 35 | 35.6 | 0 | 0 | 35.6 | 0 | 0 | 35 | 35 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.6 | 35 | 0 | 0 | 0
181 |  | RInfra-G/DPR/BP18-24/DPR No. 26.1 | In Progress |  | Refurbishment of Boiler - Eco & Re-heater | MERC/CAPEX/2018-19/061 | 2019-02-28 | 62.26 | 70:30 |  | FY 18-19 | FY 18-19 | FY 22-23 | FY 22-23 | 1. Reliability Improvement | 1.0133 | FY23: 1.46; FY24: 0.10027; Estimated FY25: 0 | 1.471% | 3.958% | 3.958% | 3.958% | 3.958% | 3.958% | 3.958% | 3.958% | 3.958% | 0.91588 | 1.5482 | 0 | 0 | [7 empty] | Projects being completed in the earliest opportunity. | [27 empty] | 175 | 0 |  |  | 0 |  |  | 35 | 35 |  |  | 35 |  |  | 35 | 35 |  |  | 35 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 35 | 35 | 0 | 0 | 0
63 |  | RInfra-G/DPR/BP18-24/DPR No. 26.2 | Completed |  | Refurbishment of Flue gas duct, Dampers & expansion bellows | MERC/CAPEX/2018-19/061 | 2019-02-28 | 2.03 | 70:30 | [6 empty] | 1.5089 | FY23: 0.12101; FY24: 0.37572; Estimated FY25: 0 | 74.33% | 74.33% | 98.8% | 98.8% | 98.8% | 98.8% | 98.8% | 98.8% | 98.8% | 1.5089 | 0 | 0.49673 | 0 | [35 empty] | 57 | 0 |  |  | 0 |  |  |  | 0.6 |  |  | 0.6 |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0.6 | 0 | 0 | 0 | 0
|  | RInfra-G/DPR/BP18-24/DPR No. 26.3 | Completed |  | Refurbishment of ESP | MERC/CAPEX/2018-19/061 | 2019-02-28 | 0.93 | 70:30 | [6 empty] | 0.54097 | FY23: 0; FY24: 0; Estimated FY25: 0 | 58.17% | 58.17% | 58.17% | 58.17% | 58.17% | 58.17% | 58.17% | 58.17% | 58.17% | 0.54097 | 0 | 0 | 0 | [39 empty] | 0 | [6 empty] | 0 |  |  | 0 | [13 empty] | 0 | [6 empty] | 0
46 |  | RInfra-G/DPR/BP18-24/DPR No. 26.4 | In Progress |  | Refurbishment of Fan silencers | MERC/CAPEX/2018-19/061 | 2019-02-28 | 1.33 | 70:30 | [6 empty] | 1.0094 | FY23: 0; FY24: 0; Estimated FY25: 0.32 | 75.9% | 75.9% | 75.9% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 99.96% | 1.0094 | 0 | 0 | 0.32 | [28 empty] | 0.46354 | 0.058259 | 0 | 0.5218 |  |  | 0.55 | 40 | 0.55 |  |  | 0.55 | [6 empty] | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | RInfra-G/DPR/BP18-24/DPR No. 26.6 | Completed |  | Strengthening of Pipe Racks | MERC/CAPEX/2018-19/061 | 2019-02-28 | 0.93 | 70:30 | [6 empty] | 0.8553 | FY23: 0.14312; FY24: 0; Estimated FY25: 0 | 91.97% | 107.4% | 107.4% | 107.4% | 107.4% | 107.4% | 107.4% | 107.4% | 107.4% | 0.8553 | 0.14312 | 0 | 0 | [39 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
[77 empty] | 0 | [6 empty] | 0
| 24 | RInfra-G/DPR/BP18-24/DPR No. 27 |  |  | Refurbishment of FGD Plant auxiliaries |  |  | 21.18 | 70:30 |  | FY 19-20 |  | FY 22-23 |  |  | 12.8799 | 0 | 1.4307 | 0.4 | 0 | 0 | 0 | 0 | 0 | 60.81% | 60.81% | 67.57% | 69.46% | 69.46% | 69.46% | 69.46% | 69.46% | 69.46% | 12.8799 | 0 | 1.4307 | 0.4 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5 | 20.5 | 0 | 0 | 20.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.5 | 0 | 0 | 0 | 0
182 |  | RInfra-G/DPR/BP18-24/DPR No. 27.1 | In Progress |  | Procurement of Booster Fan Rotor | MERC/CAPEX/2019-20/138 | 2019-05-15 | 17.58 | 70:30 |  | FY 19-20 | FY 19-20 | FY 22-23 | FY 22-23 | 1. Statutory Compliance | 11.2017 | FY23: 0; FY24: 0; Estimated FY25: 0 | 63.72% | 63.72% | 63.72% | 63.72% | 63.72% | 63.72% | 63.72% | 63.72% | 63.72% | 11.2017 | 0 | 0 | 0 | [35 empty] | 176 | 0 |  |  | 0 |  |  | 19 | 19 |  |  | 19 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 19 | 0 | 0 | 0 | 0
65 |  | RInfra-G/DPR/BP18-24/DPR No. 27.2 | In Progress |  | Refurbishment of scrubber | MERC/CAPEX/2019-20/138 | 2019-05-15 | 3.6 | 70:30 | [6 empty] | 1.6783 | FY23: 0; FY24: 1.4307; Estimated FY25: 0.4 | 46.62% | 46.62% | 86.36% | 97.47% | 97.47% | 97.47% | 97.47% | 97.47% | 97.47% | 1.6783 | 0 | 1.4307 | 0.4 | [35 empty] | 59 | 0 |  |  | 0 |  |  | 1.5 | 1.5 |  |  | 1.5 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 1.5 | 0 | 0 | 0 | 0
[77 empty] | 0 |  |  | 0 |  |  |  | 0 | [16 empty] | 0 | [6 empty] | 0
135 | 25 | RInfra-G/DPR/BP18-20/DPR No.28 | Completed |  | Refurbishment of HPT Module at DTPS | MERC/CAPEX/2018-19/04 | 2019-01-03 | 22.6 | 70:30 |  | FY 19-20 |  | FY 20-21 | FY 22-23 | 1. Efficiency Improvement | 9.3941 | [8 empty] | 41.57% | 41.57% | 41.57% | 41.57% | 41.57% | 41.57% | 41.57% | 41.57% | 41.57% | 9.3941 | 0 | 0 | 0 | [22 empty] | 22.6 |  | 22.6 | 22.6 | 0 | 22.6 | [7 empty] | 129 | 0 | [5 empty] | 0 | 0 | [6 empty] | 22.6 |  |  | 22.6 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 22.6 | 0 | 0 | 0
[80 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
136 | 26 | RInfra-G/DPR/BP18-24/DPR No.29 | In Progress |  | Refurbishment of IP Turbine | MERC/CAPEX/2019-20/118 | 2019-04-23 | 15.67 | 70:30 |  | FY 19-20 |  | FY 20-21 | FY 20-21 | 1. Reliability Improvement | 7.519 | [8 empty] | 47.98% | 47.98% | 47.98% | 47.98% | 47.98% | 47.98% | 47.98% | 47.98% | 47.98% | 7.519 | 0 | 0 | 0 | [22 empty] | 15.67 |  | 15.67 | 15.67 | 0 | 15.67 | [7 empty] | 130 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 |  |  | 0 |  |  | 15 | 15 |  |  | 15 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 15 | 0 | 0
| 27 | RInfra-G/DPR/BP18-24/DPR No.30 |  |  | Refurbishment of Turbine & its auxiliaries |  |  | 14.5 | 70:30 | [6 empty] | 3.2996 | 8.6543 | 0.50029 | 0.5 | 0 | 0 | 0 | 0 | 0 | 21.93% | 82.44% | 85.89% | 89.34% | 89.34% | 89.34% | 89.34% | 89.34% | 89.34% | 3.1796 | 8.7743 | 0.50029 | 0.5 | 0 | 0 | 0 | 0 | 0 | [34 empty] | 0 | [6 empty] | 0 | [16 empty] | 0 | [6 empty] | 0
116 |  | RInfra-G/DPR/BP18-24/DPR No.30.1 | In Progress |  | Refurbishment of Turbine Valves - spares |  |  | 8.5 | 70:30 | [6 empty] | 0.030891 | FY23: 7.1535; FY24: 0.50029; Estimated FY25: 0 | 0% | 84.52% | 90.41% | 90.41% | 90.41% | 90.41% | 90.41% | 90.41% | 90.41% | 0 | 7.1843 | 0.50029 | 0 | [35 empty] | 110 | 0 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 8.5 |  |  | 8.5 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 8.5 | 0 | 0
|  | RInfra-G/DPR/BP18-24/DPR No.30.2 | In Progress |  | Refurbishment of BFP Hydraulic coupling |  |  | 5 | 70:30 | [6 empty] | 3.1796 | FY23: 1.0613; FY24: 0; Estimated FY25: 0 | 63.59% | 84.82% | 84.82% | 84.82% | 84.82% | 84.82% | 84.82% | 84.82% | 84.82% | 3.1796 | 1.0613 | 0 | 0 | [35 empty] | 225 | 0 |  |  | 0 | [6 empty] | 0 |  |  |  | 1.2 |  |  | 1.2 |  |  |  | 3.75 |  |  | 3.75 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 1.2 | 3.75 | 0 | 0
62 |  | RInfra-G/DPR/BP18-24/DPR No.30.3 | In Progress |  | Refurbishment of EOT cranes and Hoists |  |  | 1 | 70:30 | [6 empty] | 0.089141 | FY23: 0.4395; FY24: 0; Estimated FY25: 0.5 | 0% | 52.86% | 52.86% | 102.9% | 102.9% | 102.9% | 102.9% | 102.9% | 102.9% | 0 | 0.52864 | 0 | 0.5 | [35 empty] | 56 | 0 |  |  | 0 | [6 empty] | 0 |  |  |  | 0.5 |  |  | 0.5 |  |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 0.5 | 0 | 0 | 0
|  | Total DPR In-Principle Apprval received | [5 empty] | 835.558 | [7 empty] | 382.6937 | 24.5109 | 6.8708 | 1.4436 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 382.3591 | 20.4573 | 11.1331 | 1.47 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 121.0431 | 115.7139 | 2.9774 | 0 | 65.4718 | 0.65739 | 0 | 66.1292 | 4.2386 | 38.27 | 0 | 42.4994 | 41.9755 | 4.2386 | 38.27 | 22.432 | 2.0087 | 0.52624 | 24.967 | 1.9528 | 1.9528 | 41.2393 |  | 44.2053 | 0 | 0 | 44.2053 | [17 empty] | 27.29 | [6 empty] | 47 | [7 empty] | 0 | 0 | #REF!
| 28 | DPRs to be submitted for approval | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Life extension of Mechanical systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Life extension of Electrical systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Life extension of Control & Instrumentation systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Life extension of Civil structures | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Life extension of Coal Handling plant systems | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
78 |  |  |  |  | TOTAL | [11 empty] | 24.5109 | 6.8708 | 1.4436 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 20.4573 | 11.1331 | 1.47 | 0 | 0 | 0 | 0 | 0 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 29 | Non DPR Schemes | [14 empty] | 6.0169 | 25.704 | 48.6 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 5.7654 | 24.7074 | 48.6 | 0 | 0 | 0 | 0 | 0 | [59 empty] | 82
| 30 | Capex Inventory | [14 empty] | 4.5834 | 0.5181 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 31 | Total | [14 empty] | 35.1112 | 33.0929 | 50.0436 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 26.2227 | 35.8405 | 50.07 | 0 | 0 | 0 | 0 | 0